## D02_Model
MODEL_CODE | MODEL_NAME | PRODUCT_GROUP_CODE | PRODUCT_GROUP_NAME | BASE_MODEL_CODE | MODEL_LEVEL | MODEL_TYPE | DEV_GRADE | PROJECT_CODE | PROJECT_STATUS | MODEL_STATUS | OS_MODEL_FLAG | PROJECT_DROP_FLAG | MP_CREATION_DATE
WASH_F_001 | Synthetic 드럼세탁기 Model-001 Grade-T2 | FL | 드럼세탁기 |  | 1 | Base | T2 | SYN_PJT_01 | Completed | 완료 | N | N | 2025-08-18
WASH_T_002 | Synthetic 통돌이세탁기 Model-002 Grade-T1 | TL | 통돌이세탁기 |  | 1 | Base | T1 | SYN_PJT_02 | Running | 진행중 | N | N | 2026-03-30
DRY_X_003 | Synthetic 건조기 Model-003 Grade-T2 | DR | 건조기 |  | 1 | Base | T2 | SYN_PJT_03 | Running | 진행중 | N | N | 2026-03-23
TWR_Z_004 | Synthetic 워시타워 Model-004 Grade-B | WT | 워시타워 |  | 1 | Base | B | SYN_PJT_03 | Running | 진행중 | N | N | 2026-06-01
WASH_F_005 | Synthetic 드럼세탁기 Model-005 Grade-S | FL | 드럼세탁기 |  | 1 | Base | S | SYN_PJT_03 | Running | 진행중 | N | N | 2026-05-25
WASH_T_006 | Synthetic 통돌이세탁기 Model-006 Grade-A | TL | 통돌이세탁기 |  | 1 | Base | A | SYN_PJT_03 | Running | 진행중 | N | N | 2026-04-27
DRY_X_007 | Synthetic 건조기 Model-007 Grade-S | DR | 건조기 |  | 1 | Base | S | SYN_PJT_01 | Running | 진행중 | N | N | 2026-04-20
TWR_Z_008 | Synthetic 워시타워 Model-008 Grade-A | WT | 워시타워 |  | 1 | Base | A | SYN_PJT_04 | Running | 진행중 | N | N | 2026-05-04
WASH_F_009 | Synthetic 드럼세탁기 Model-009 Grade-S | FL | 드럼세탁기 |  | 1 | Base | S | SYN_PJT_05 | Completed | 완료 | N | N | 2025-11-10
WASH_T_010 | Synthetic 통돌이세탁기 Model-010 Grade-B | TL | 통돌이세탁기 |  | 1 | Base | B | SYN_PJT_03 | Running | 진행중 | N | N | 2026-06-08
DRY_X_011 | Synthetic 건조기 Model-011 Grade-Cb | DR | 건조기 |  | 1 | Base | Cb | SYN_PJT_05 | Running | 진행중 | N | N | 2026-04-06
TWR_Z_012 | Synthetic 워시타워 Model-012 Grade-Cb | WT | 워시타워 |  | 1 | Base | Cb | SYN_PJT_06 | Completed | 완료 | N | N | 2026-01-05
WASH_F_013 | Synthetic 드럼세탁기 Model-013 Grade-B | FL | 드럼세탁기 |  | 1 | Base | B | SYN_PJT_07 | Running | 진행중 | N | Y | 2026-05-11
WASH_T_014 | Synthetic 통돌이세탁기 Model-014 Grade-Cb | TL | 통돌이세탁기 |  | 1 | Base | Cb | SYN_PJT_08 | Completed | 완료 | N | N | 2026-01-19
DRY_X_015 | Synthetic 건조기 Model-015 Grade-A | DR | 건조기 |  | 1 | Base | A | SYN_PJT_03 | Completed | 완료 | N | N | 2025-08-18
TWR_Z_016 | Synthetic 워시타워 Model-016 Grade-T1 | WT | 워시타워 |  | 1 | Base | T1 | SYN_PJT_09 | Running | 진행중 | N | N | 2026-03-23
WASH_F_017 | Synthetic 드럼세탁기 Model-017 Grade-A | FL | 드럼세탁기 |  | 1 | Base | A | SYN_PJT_10 | Completed | 완료 | N | N | 2025-09-08
WASH_T_018 | Synthetic 통돌이세탁기 Model-018 Grade-B | TL | 통돌이세탁기 |  | 1 | Base | B | SYN_PJT_05 | Running | 진행중 | N | N | 2026-03-23
DRY_X_019 | Synthetic 건조기 Model-019 Grade-T2 | DR | 건조기 |  | 1 | Base | T2 | SYN_PJT_09 | Completed | 완료 | N | N | 2025-08-25
TWR_Z_020 | Synthetic 워시타워 Model-020 Grade-Cc | WT | 워시타워 |  | 1 | Base | Cc | SYN_PJT_02 | Running | 진행중 | N | N | 2026-06-15
WASH_F_021 | Synthetic 드럼세탁기 Model-021 Grade-T2 | FL | 드럼세탁기 |  | 1 | Base | T2 | SYN_PJT_05 | Running | 진행중 | N | N | 2026-05-18
WASH_T_022 | Synthetic 통돌이세탁기 Model-022 Grade-T3 | TL | 통돌이세탁기 |  | 1 | Base | T3 | SYN_PJT_09 | Completed | 완료 | N | N | 2025-10-27
DRY_X_023 | Synthetic 건조기 Model-023 Grade-T3 | DR | 건조기 |  | 1 | Base | T3 | SYN_PJT_11 | Completed | 완료 | N | N | 2025-12-22
TWR_Z_024 | Synthetic 워시타워 Model-024 Grade-S | WT | 워시타워 |  | 1 | Base | S | SYN_PJT_07 | Completed | 완료 | N | N | 2025-10-27
WASH_F_025 | Synthetic 드럼세탁기 Model-025 Grade-T3 | FL | 드럼세탁기 | WASH_F_001 | 2 | 파생 | T3 | SYN_PJT_11 | Completed | 완료 | N | N | 2025-11-10
WASH_T_026 | Synthetic 통돌이세탁기 Model-026 Grade-Ca | TL | 통돌이세탁기 | WASH_T_002 | 2 | 파생 | Ca | SYN_PJT_07 | Running | 진행중 | N | N | 2026-04-13
DRY_X_027 | Synthetic 건조기 Model-027 Grade-Cb | DR | 건조기 | DRY_X_003 | 2 | 파생 | Cb | SYN_PJT_06 | Completed | 완료 | N | N | 2025-09-22
TWR_Z_028 | Synthetic 워시타워 Model-028 Grade-D | WT | 워시타워 | TWR_Z_004 | 2 | 파생 | D | SYN_PJT_05 | Running | 진행중 | N | N | 2026-04-20
WASH_F_029 | Synthetic 드럼세탁기 Model-029 Grade-Cc | FL | 드럼세탁기 | WASH_F_005 | 2 | 파생 | Cc | SYN_PJT_06 | Running | 진행중 | Y | N | 2026-05-04
WASH_T_030 | Synthetic 통돌이세탁기 Model-030 Grade-B | TL | 통돌이세탁기 | WASH_T_006 | 2 | 파생 | B | SYN_PJT_04 | Completed | 완료 | N | N | 2026-01-19
DRY_X_031 | Synthetic 건조기 Model-031 Grade-B | DR | 건조기 | DRY_X_007 | 2 | 파생 | B | SYN_PJT_10 | Completed | 완료 | N | N | 2025-09-01
TWR_Z_032 | Synthetic 워시타워 Model-032 Grade-Cc | WT | 워시타워 | TWR_Z_008 | 2 | 파생 | Cc | SYN_PJT_01 | Running | 진행중 | N | N | 2026-06-08
WASH_F_033 | Synthetic 드럼세탁기 Model-033 Grade-Cc | FL | 드럼세탁기 | WASH_F_009 | 2 | 파생 | Cc | SYN_PJT_03 | Running | 진행중 | N | N | 2026-05-11
WASH_T_034 | Synthetic 통돌이세탁기 Model-034 Grade-T1 | TL | 통돌이세탁기 | WASH_T_010 | 2 | 파생 | T1 | SYN_PJT_08 | Running | 진행중 | N | N | 2026-05-18
DRY_X_035 | Synthetic 건조기 Model-035 Grade-A | DR | 건조기 | DRY_X_011 | 2 | 파생 | A | SYN_PJT_05 | Running | 진행중 | N | N | 2026-04-13
TWR_Z_036 | Synthetic 워시타워 Model-036 Grade-Cb | WT | 워시타워 | TWR_Z_012 | 2 | 파생 | Cb | SYN_PJT_10 | Completed | 완료 | N | N | 2025-07-14
WASH_F_037 | Synthetic 드럼세탁기 Model-037 Grade-A | FL | 드럼세탁기 | WASH_F_013 | 2 | 파생 | A | SYN_PJT_04 | Running | 진행중 | N | Y | 2026-05-18
WASH_T_038 | Synthetic 통돌이세탁기 Model-038 Grade-Cb | TL | 통돌이세탁기 | WASH_T_014 | 2 | 파생 | Cb | SYN_PJT_01 | Completed | 완료 | N | N | 2025-08-11
DRY_X_039 | Synthetic 건조기 Model-039 Grade-S | DR | 건조기 | DRY_X_015 | 2 | 파생 | S | SYN_PJT_03 | Completed | 완료 | N | N | 2025-11-24
TWR_Z_040 | Synthetic 워시타워 Model-040 Grade-Cc | WT | 워시타워 | TWR_Z_016 | 2 | 파생 | Cc | SYN_PJT_03 | Completed | 완료 | N | N | 2025-09-01
WASH_F_041 | Synthetic 드럼세탁기 Model-041 Grade-D | FL | 드럼세탁기 | WASH_F_017 | 2 | 파생 | D | SYN_PJT_12 | Completed | 완료 | N | N | 2026-02-09
WASH_T_042 | Synthetic 통돌이세탁기 Model-042 Grade-A | TL | 통돌이세탁기 | WASH_T_018 | 2 | 파생 | A | SYN_PJT_04 | Running | 진행중 | N | N | 2026-05-18
DRY_X_043 | Synthetic 건조기 Model-043 Grade-Cb | DR | 건조기 | DRY_X_019 | 2 | 파생 | Cb | SYN_PJT_09 | Completed | 완료 | N | N | 2025-11-24
TWR_Z_044 | Synthetic 워시타워 Model-044 Grade-D | WT | 워시타워 | TWR_Z_020 | 2 | 파생 | D | SYN_PJT_02 | Running | 진행중 | N | N | 2026-03-30
WASH_F_045 | Synthetic 드럼세탁기 Model-045 Grade-D | FL | 드럼세탁기 | WASH_F_021 | 2 | 파생 | D | SYN_PJT_03 | Completed | 완료 | N | N | 2025-08-04
WASH_T_046 | Synthetic 통돌이세탁기 Model-046 Grade-T2 | TL | 통돌이세탁기 | WASH_T_022 | 2 | 파생 | T2 | SYN_PJT_05 | Running | 진행중 | N | N | 2026-05-25
DRY_X_047 | Synthetic 건조기 Model-047 Grade-Ca | DR | 건조기 | DRY_X_023 | 2 | 파생 | Ca | SYN_PJT_10 | Completed | 완료 | N | N | 2025-12-15
TWR_Z_048 | Synthetic 워시타워 Model-048 Grade-A | WT | 워시타워 | TWR_Z_024 | 2 | 파생 | A | SYN_PJT_02 | Running | 진행중 | N | N | 2026-05-18
WASH_F_049 | Synthetic 드럼세탁기 Model-049 Grade-S | FL | 드럼세탁기 | WASH_F_001 | 2 | 파생 | S | SYN_PJT_06 | Completed | 완료 | N | N | 2025-11-03
WASH_T_050 | Synthetic 통돌이세탁기 Model-050 Grade-Cb | TL | 통돌이세탁기 | WASH_T_002 | 2 | 파생 | Cb | SYN_PJT_03 | Running | 진행중 | N | N | 2026-03-30
DRY_X_051 | Synthetic 건조기 Model-051 Grade-S | DR | 건조기 | DRY_X_003 | 2 | 파생 | S | SYN_PJT_11 | Running | 진행중 | N | N | 2026-05-11
TWR_Z_052 | Synthetic 워시타워 Model-052 Grade-S | WT | 워시타워 | TWR_Z_004 | 2 | 파생 | S | SYN_PJT_02 | Running | 진행중 | N | N | 2026-03-23
WASH_F_053 | Synthetic 드럼세탁기 Model-053 Grade-T3 | FL | 드럼세탁기 | WASH_F_005 | 2 | 파생 | T3 | SYN_PJT_09 | Completed | 완료 | N | N | 2025-09-01
WASH_T_054 | Synthetic 통돌이세탁기 Model-054 Grade-S | TL | 통돌이세탁기 | WASH_T_006 | 2 | 파생 | S | SYN_PJT_05 | Completed | 완료 | N | N | 2025-09-08
DRY_X_055 | Synthetic 건조기 Model-055 Grade-B | DR | 건조기 | DRY_X_007 | 2 | 파생 | B | SYN_PJT_05 | Running | 진행중 | N | N | 2026-06-15
TWR_Z_056 | Synthetic 워시타워 Model-056 Grade-A | WT | 워시타워 | TWR_Z_008 | 2 | 파생 | A | SYN_PJT_12 | Running | 진행중 | N | N | 2026-04-13
WASH_F_057 | Synthetic 드럼세탁기 Model-057 Grade-Ca | FL | 드럼세탁기 | WASH_F_009 | 2 | 파생 | Ca | SYN_PJT_11 | Completed | 완료 | N | N | 2025-07-28
WASH_T_058 | Synthetic 통돌이세탁기 Model-058 Grade-B | TL | 통돌이세탁기 | WASH_T_010 | 2 | 파생 | B | SYN_PJT_03 | Completed | 완료 | N | N | 2025-07-28
DRY_X_059 | Synthetic 건조기 Model-059 Grade-T3 | DR | 건조기 | DRY_X_011 | 2 | 파생 | T3 | SYN_PJT_04 | Running | 진행중 | N | N | 2026-05-18
TWR_Z_060 | Synthetic 워시타워 Model-060 Grade-D | WT | 워시타워 | TWR_Z_012 | 2 | 파생 | D | SYN_PJT_04 | Running | 진행중 | N | N | 2026-05-18
WASH_F_061 | Synthetic 드럼세탁기 Model-061 Grade-Cc | FL | 드럼세탁기 | WASH_F_013 | 2 | 파생 | Cc | SYN_PJT_02 | Running | 진행중 | N | N | 2026-05-25
WASH_T_062 | Synthetic 통돌이세탁기 Model-062 Grade-B | TL | 통돌이세탁기 | WASH_T_014 | 2 | 파생 | B | SYN_PJT_12 | Completed | 완료 | N | N | 2026-01-19
DRY_X_063 | Synthetic 건조기 Model-063 Grade-T3 | DR | 건조기 | DRY_X_015 | 2 | 파생 | T3 | SYN_PJT_03 | Completed | 완료 | N | N | 2025-09-08
TWR_Z_064 | Synthetic 워시타워 Model-064 Grade-Ca | WT | 워시타워 | TWR_Z_016 | 2 | 파생 | Ca | SYN_PJT_10 | Completed | 완료 | N | N | 2025-08-04
WASH_F_065 | Synthetic 드럼세탁기 Model-065 Grade-T2 | FL | 드럼세탁기 | WASH_F_017 | 2 | 파생 | T2 | SYN_PJT_07 | Completed | 완료 | N | N | 2025-08-25
WASH_T_066 | Synthetic 통돌이세탁기 Model-066 Grade-Cb | TL | 통돌이세탁기 | WASH_T_018 | 2 | 파생 | Cb | SYN_PJT_09 | Running | 진행중 | N | N | 2026-06-01
DRY_X_067 | Synthetic 건조기 Model-067 Grade-T2 | DR | 건조기 | DRY_X_019 | 2 | 파생 | T2 | SYN_PJT_10 | Completed | 완료 | N | N | 2025-07-21
TWR_Z_068 | Synthetic 워시타워 Model-068 Grade-Cb | WT | 워시타워 | TWR_Z_020 | 2 | 파생 | Cb | SYN_PJT_05 | Running | 진행중 | N | N | 2026-04-27
WASH_F_069 | Synthetic 드럼세탁기 Model-069 Grade-Cb | FL | 드럼세탁기 | WASH_F_021 | 2 | 파생 | Cb | SYN_PJT_08 | Completed | 완료 | N | N | 2025-07-28
WASH_T_070 | Synthetic 통돌이세탁기 Model-070 Grade-T2 | TL | 통돌이세탁기 | WASH_T_022 | 2 | 파생 | T2 | SYN_PJT_09 | Completed | 완료 | N | N | 2026-01-19
DRY_X_071 | Synthetic 건조기 Model-071 Grade-B | DR | 건조기 | DRY_X_023 | 2 | 파생 | B | SYN_PJT_01 | Completed | 완료 | N | N | 2025-07-28
TWR_Z_072 | Synthetic 워시타워 Model-072 Grade-Cb | WT | 워시타워 | TWR_Z_024 | 2 | 파생 | Cb | SYN_PJT_01 | Running | 진행중 | N | N | 2026-04-20
WASH_F_073 | Synthetic 드럼세탁기 Model-073 Grade-T3 | FL | 드럼세탁기 | WASH_F_001 | 2 | 파생 | T3 | SYN_PJT_11 | Completed | 완료 | N | N | 2025-10-06
WASH_T_074 | Synthetic 통돌이세탁기 Model-074 Grade-Cc | TL | 통돌이세탁기 | WASH_T_002 | 2 | 파생 | Cc | SYN_PJT_11 | Completed | 완료 | N | N | 2026-01-26
DRY_X_075 | Synthetic 건조기 Model-075 Grade-A | DR | 건조기 | DRY_X_003 | 2 | 파생 | A | SYN_PJT_07 | Completed | 완료 | N | N | 2026-01-12
TWR_Z_076 | Synthetic 워시타워 Model-076 Grade-T3 | WT | 워시타워 | TWR_Z_004 | 2 | 파생 | T3 | SYN_PJT_02 | Completed | 완료 | N | N | 2025-12-29
WASH_F_077 | Synthetic 드럼세탁기 Model-077 Grade-Cb | FL | 드럼세탁기 | WASH_F_025 | 3 | 파생 | Cb | SYN_PJT_12 | Running | 진행중 | N | N | 2026-05-25
WASH_T_078 | Synthetic 통돌이세탁기 Model-078 Grade-S | TL | 통돌이세탁기 | WASH_T_026 | 3 | 파생 | S | SYN_PJT_03 | Completed | 완료 | N | N | 2025-12-01
DRY_X_079 | Synthetic 건조기 Model-079 Grade-A | DR | 건조기 | DRY_X_027 | 3 | 파생 | A | SYN_PJT_05 | Completed | 완료 | N | N | 2025-12-22
TWR_Z_080 | Synthetic 워시타워 Model-080 Grade-T3 | WT | 워시타워 | TWR_Z_028 | 3 | 파생 | T3 | SYN_PJT_02 | Running | 진행중 | N | N | 2026-06-15
WASH_F_081 | Synthetic 드럼세탁기 Model-081 Grade-A | FL | 드럼세탁기 | WASH_F_029 | 3 | 파생 | A | SYN_PJT_03 | Completed | 완료 | N | N | 2025-08-18
WASH_T_082 | Synthetic 통돌이세탁기 Model-082 Grade-T3 | TL | 통돌이세탁기 | WASH_T_030 | 3 | 파생 | T3 | SYN_PJT_12 | Running | 진행중 | N | N | 2026-06-15
DRY_X_083 | Synthetic 건조기 Model-083 Grade-T3 | DR | 건조기 | DRY_X_031 | 3 | 파생 | T3 | SYN_PJT_03 | Completed | 완료 | N | N | 2025-12-15
TWR_Z_084 | Synthetic 워시타워 Model-084 Grade-T1 | WT | 워시타워 | TWR_Z_032 | 3 | 파생 | T1 | SYN_PJT_07 | Completed | 완료 | N | N | 2025-10-06
WASH_F_085 | Synthetic 드럼세탁기 Model-085 Grade-Cb | FL | 드럼세탁기 | WASH_F_033 | 3 | 파생 | Cb | SYN_PJT_07 | Running | 진행중 | Y | N | 2026-04-06
WASH_T_086 | Synthetic 통돌이세탁기 Model-086 Grade-Ca | TL | 통돌이세탁기 | WASH_T_034 | 3 | 파생 | Ca | SYN_PJT_09 | Completed | 완료 | N | N | 2025-12-08
DRY_X_087 | Synthetic 건조기 Model-087 Grade-B | DR | 건조기 | DRY_X_035 | 3 | 파생 | B | SYN_PJT_08 | Completed | 완료 | N | N | 2025-12-01
TWR_Z_088 | Synthetic 워시타워 Model-088 Grade-T2 | WT | 워시타워 | TWR_Z_036 | 3 | 파생 | T2 | SYN_PJT_08 | Completed | 완료 | N | N | 2026-02-09
WASH_F_089 | Synthetic 드럼세탁기 Model-089 Grade-T3 | FL | 드럼세탁기 | WASH_F_037 | 3 | 파생 | T3 | SYN_PJT_02 | Completed | 완료 | N | N | 2025-12-29
WASH_T_090 | Synthetic 통돌이세탁기 Model-090 Grade-Cc | TL | 통돌이세탁기 | WASH_T_038 | 3 | 파생 | Cc | SYN_PJT_07 | Running | 진행중 | N | N | 2026-04-20
DRY_X_091 | Synthetic 건조기 Model-091 Grade-T2 | DR | 건조기 | DRY_X_039 | 3 | 파생 | T2 | SYN_PJT_12 | Running | 진행중 | N | Y | 2026-06-01
TWR_Z_092 | Synthetic 워시타워 Model-092 Grade-Ca | WT | 워시타워 | TWR_Z_040 | 3 | 파생 | Ca | SYN_PJT_08 | Running | 진행중 | N | Y | 2026-04-27
WASH_F_093 | Synthetic 드럼세탁기 Model-093 Grade-Cc | FL | 드럼세탁기 | WASH_F_041 | 3 | 파생 | Cc | SYN_PJT_10 | Completed | 완료 | N | N | 2026-01-26
WASH_T_094 | Synthetic 통돌이세탁기 Model-094 Grade-B | TL | 통돌이세탁기 | WASH_T_042 | 3 | 파생 | B | SYN_PJT_05 | Completed | 완료 | N | N | 2025-10-20
DRY_X_095 | Synthetic 건조기 Model-095 Grade-T2 | DR | 건조기 | DRY_X_043 | 3 | 파생 | T2 | SYN_PJT_07 | Running | 진행중 | N | N | 2026-03-30
TWR_Z_096 | Synthetic 워시타워 Model-096 Grade-Cc | WT | 워시타워 | TWR_Z_044 | 3 | 파생 | Cc | SYN_PJT_07 | Running | 진행중 | N | N | 2026-04-13
WASH_F_097 | Synthetic 드럼세탁기 Model-097 Grade-B | FL | 드럼세탁기 | WASH_F_045 | 3 | 파생 | B | SYN_PJT_02 | Running | 진행중 | Y | N | 2026-04-06
WASH_T_098 | Synthetic 통돌이세탁기 Model-098 Grade-Cc | TL | 통돌이세탁기 | WASH_T_046 | 3 | 파생 | Cc | SYN_PJT_06 | Completed | 완료 | N | N | 2026-02-09
DRY_X_099 | Synthetic 건조기 Model-099 Grade-T1 | DR | 건조기 | DRY_X_047 | 3 | 파생 | T1 | SYN_PJT_06 | Running | 진행중 | N | N | 2026-06-08
TWR_Z_100 | Synthetic 워시타워 Model-100 Grade-T2 | WT | 워시타워 | TWR_Z_048 | 3 | 파생 | T2 | SYN_PJT_03 | Completed | 완료 | N | N | 2025-08-18

## D07_PreMPWaterfall
MODEL_CODE | PLAN_WEEK | PLAN_WEEK_SEQ | WEEKS_TO_PREMP_SYSTEM | PREMP_INITIAL_WEEK | PREMP_SYSTEM_WEEK | PREMP_SYSTEM_DATE | PREMP_PREDICT_WEEK | PREMP_PREDICT_DATE | PREMP_ACTUAL_WEEK | DELAY_INITIAL_VS_LATEST | DELAY_SYSTEM_VS_PREDICT | ANOMALY_GRADE | KEY_FACTOR
WASH_F_001 | 2025W41 | 41 | 12 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W42 | 42 | 11 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_001 | 2025W43 | 43 | 10 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W44 | 44 | 9 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_001 | 2025W45 | 45 | 8 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W46 | 46 | 7 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W47 | 47 | 6 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W48 | 48 | 5 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_001 | 2025W49 | 49 | 4 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_001 | 2025W50 | 50 | 3 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_001 | 2025W51 | 51 | 2 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2025W52 | 52 | 1 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_001 | 2026W01 | 53 | 0 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_001 | 2026W02 | 54 | 1 | 2026W01 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 2 | 0 | 정상
WASH_F_001 | 2026W03 | 55 | 0 | 2026W01 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 2 | 0 | 정상
WASH_F_001 | 2026W04 | 56 | -1 | 2026W01 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 2 | 0 | 정상
WASH_F_001 | 2026W05 | 57 | -2 | 2026W01 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 2 | 0 | 정상
WASH_T_002 | 2026W21 | 73 | 12 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W22 | 74 | 11 | 2026W33 | 2026W33 | 2026-08-17 | 2026W32 | 2026-08-10 |  | 0 | -1 | 정상
WASH_T_002 | 2026W23 | 75 | 10 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W24 | 76 | 9 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W25 | 77 | 8 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W26 | 78 | 7 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W27 | 79 | 6 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W28 | 80 | 5 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W29 | 81 | 4 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W30 | 82 | 3 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W31 | 83 | 2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W32 | 84 | 1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W33 | 85 | 0 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W34 | 86 | -1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_T_002 | 2026W35 | 87 | -2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
DRY_X_003 | 2026W20 | 72 | 12 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
DRY_X_003 | 2026W21 | 73 | 11 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
DRY_X_003 | 2026W22 | 74 | 10 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W23 | 75 | 9 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W24 | 76 | 8 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W25 | 77 | 7 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W26 | 78 | 6 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W27 | 79 | 5 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W28 | 80 | 4 | 2026W32 | 2026W32 | 2026-08-10 | 2026W33 | 2026-08-17 |  | 0 | 1 | 정상
DRY_X_003 | 2026W29 | 81 | 4 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W30 | 82 | 3 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W31 | 83 | 2 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W32 | 84 | 1 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W33 | 85 | 0 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W34 | 86 | -1 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
DRY_X_003 | 2026W35 | 87 | -2 | 2026W32 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 1 | 0 | 정상
TWR_Z_004 | 2026W30 | 82 | 12 | 2026W42 | 2026W42 | 2026-10-19 | 2026W43 | 2026-10-26 |  | 0 | 1 | 정상
TWR_Z_004 | 2026W31 | 83 | 11 | 2026W42 | 2026W42 | 2026-10-19 | 2026W43 | 2026-10-26 |  | 0 | 1 | 정상
TWR_Z_004 | 2026W32 | 84 | 10 | 2026W42 | 2026W42 | 2026-10-19 | 2026W44 | 2026-11-02 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_004 | 2026W33 | 85 | 9 | 2026W42 | 2026W42 | 2026-10-19 | 2026W44 | 2026-11-02 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_004 | 2026W34 | 86 | 8 | 2026W42 | 2026W42 | 2026-10-19 | 2026W44 | 2026-11-02 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_004 | 2026W35 | 87 | 7 | 2026W42 | 2026W42 | 2026-10-19 | 2026W44 | 2026-11-02 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_004 | 2026W36 | 88 | 6 | 2026W42 | 2026W42 | 2026-10-19 | 2026W44 | 2026-11-02 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_005 | 2026W29 | 81 | 12 | 2026W41 | 2026W41 | 2026-10-12 | 2026W40 | 2026-10-05 |  | 0 | -1 | 정상
WASH_F_005 | 2026W30 | 82 | 11 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W31 | 83 | 10 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W32 | 84 | 9 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W33 | 85 | 8 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W34 | 86 | 7 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W35 | 87 | 6 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_F_005 | 2026W36 | 88 | 5 | 2026W41 | 2026W41 | 2026-10-12 | 2026W41 | 2026-10-12 |  | 0 | 0 | 정상
WASH_T_006 | 2026W25 | 77 | 12 | 2026W37 | 2026W37 | 2026-09-14 | 2026W41 | 2026-10-12 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_006 | 2026W26 | 78 | 11 | 2026W37 | 2026W37 | 2026-09-14 | 2026W41 | 2026-10-12 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_006 | 2026W27 | 79 | 10 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W28 | 80 | 9 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W29 | 81 | 8 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W30 | 82 | 7 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W31 | 83 | 6 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 양산검증(PV) 지연 요소
WASH_T_006 | 2026W32 | 84 | 5 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W33 | 85 | 4 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 공정/부품 리드타임 지연
WASH_T_006 | 2026W34 | 86 | 3 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W35 | 87 | 2 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_006 | 2026W36 | 88 | 1 | 2026W37 | 2026W37 | 2026-09-14 | 2026W42 | 2026-10-19 |  | 0 | 5 | 심각 | 양산검증(PV) 지연 요소
DRY_X_007 | 2026W24 | 76 | 12 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W25 | 77 | 11 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W26 | 78 | 10 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W27 | 79 | 9 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W28 | 80 | 8 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W29 | 81 | 7 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W30 | 82 | 6 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W31 | 83 | 5 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W32 | 84 | 4 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W33 | 85 | 3 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W34 | 86 | 2 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W35 | 87 | 1 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
DRY_X_007 | 2026W36 | 88 | 0 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_008 | 2026W26 | 78 | 12 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_008 | 2026W27 | 79 | 11 | 2026W38 | 2026W38 | 2026-09-21 | 2026W43 | 2026-10-26 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W28 | 80 | 10 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W29 | 81 | 9 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W30 | 82 | 8 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W31 | 83 | 7 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W32 | 84 | 6 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_008 | 2026W33 | 85 | 5 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W34 | 86 | 4 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W35 | 87 | 3 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_008 | 2026W36 | 88 | 2 | 2026W38 | 2026W38 | 2026-09-21 | 2026W44 | 2026-11-02 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_F_009 | 2026W01 | 53 | 12 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W02 | 54 | 11 | 2026W13 | 2026W13 | 2026-03-30 | 2026W12 | 2026-03-23 | 2026W13 | 0 | -1 | 정상
WASH_F_009 | 2026W03 | 55 | 10 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W04 | 56 | 9 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W05 | 57 | 8 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W06 | 58 | 7 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W07 | 59 | 6 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W08 | 60 | 5 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W09 | 61 | 4 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W10 | 62 | 3 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W11 | 63 | 2 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W12 | 64 | 1 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W13 | 65 | 0 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W14 | 66 | -1 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_F_009 | 2026W15 | 67 | -2 | 2026W13 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 0 | 정상
WASH_T_010 | 2026W31 | 83 | 12 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_010 | 2026W32 | 84 | 11 | 2026W43 | 2026W43 | 2026-10-26 | 2026W46 | 2026-11-16 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_010 | 2026W33 | 85 | 10 | 2026W43 | 2026W43 | 2026-10-26 | 2026W46 | 2026-11-16 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_010 | 2026W34 | 86 | 9 | 2026W43 | 2026W43 | 2026-10-26 | 2026W46 | 2026-11-16 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_010 | 2026W35 | 87 | 8 | 2026W43 | 2026W43 | 2026-10-26 | 2026W46 | 2026-11-16 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_010 | 2026W36 | 88 | 7 | 2026W43 | 2026W43 | 2026-10-26 | 2026W46 | 2026-11-16 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_011 | 2026W22 | 74 | 12 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
DRY_X_011 | 2026W23 | 75 | 11 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
DRY_X_011 | 2026W24 | 76 | 10 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W25 | 77 | 9 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W26 | 78 | 8 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W27 | 79 | 7 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W28 | 80 | 6 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W29 | 81 | 5 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W30 | 82 | 4 | 2026W34 | 2026W34 | 2026-08-24 | 2026W35 | 2026-08-31 |  | 0 | 1 | 정상
DRY_X_011 | 2026W31 | 83 | 4 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
DRY_X_011 | 2026W32 | 84 | 3 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
DRY_X_011 | 2026W33 | 85 | 2 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
DRY_X_011 | 2026W34 | 86 | 1 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
DRY_X_011 | 2026W35 | 87 | 0 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
DRY_X_011 | 2026W36 | 88 | -1 | 2026W34 | 2026W35 | 2026-08-31 | 2026W35 | 2026-08-31 |  | 1 | 0 | 정상
TWR_Z_012 | 2026W09 | 61 | 12 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_012 | 2026W10 | 62 | 11 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
TWR_Z_012 | 2026W11 | 63 | 10 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_012 | 2026W12 | 64 | 9 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_012 | 2026W13 | 65 | 8 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_012 | 2026W14 | 66 | 7 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
TWR_Z_012 | 2026W15 | 67 | 6 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_012 | 2026W16 | 68 | 5 | 2026W21 | 2026W21 | 2026-05-25 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_012 | 2026W17 | 69 | 6 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W18 | 70 | 5 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W19 | 71 | 4 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W20 | 72 | 3 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W21 | 73 | 2 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W22 | 74 | 1 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W23 | 75 | 0 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W24 | 76 | -1 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
TWR_Z_012 | 2026W25 | 77 | -2 | 2026W21 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 2 | 0 | 정상
WASH_F_013 | 2026W27 | 79 | 12 | 2026W39 | 2026W39 | 2026-09-28 | 2026W39 | 2026-09-28 |  | 0 | 0 | 정상
WASH_F_013 | 2026W28 | 80 | 11 | 2026W39 | 2026W39 | 2026-09-28 | 2026W39 | 2026-09-28 |  | 0 | 0 | 정상
WASH_F_013 | 2026W29 | 81 | 10 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W30 | 82 | 9 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W31 | 83 | 8 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W32 | 84 | 7 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W33 | 85 | 6 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W34 | 86 | 5 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W35 | 87 | 4 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_013 | 2026W36 | 88 | 3 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_T_014 | 2026W11 | 63 | 12 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W12 | 64 | 11 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W13 | 65 | 10 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W14 | 66 | 9 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W15 | 67 | 8 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W16 | 68 | 7 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W17 | 69 | 6 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W18 | 70 | 5 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W19 | 71 | 4 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W20 | 72 | 3 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W21 | 73 | 2 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W22 | 74 | 1 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W23 | 75 | 0 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W24 | 76 | -1 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
WASH_T_014 | 2026W25 | 77 | -2 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 0 | 정상
DRY_X_015 | 2025W41 | 41 | 12 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W04 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W42 | 42 | 11 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W43 | 43 | 10 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W44 | 44 | 9 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W45 | 45 | 8 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W46 | 46 | 7 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W47 | 47 | 6 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W48 | 48 | 5 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_015 | 2025W49 | 49 | 4 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_015 | 2025W50 | 50 | 3 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_015 | 2025W51 | 51 | 5 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2025W52 | 52 | 4 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W01 | 53 | 3 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W02 | 54 | 2 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W03 | 55 | 1 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W04 | 56 | 0 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W05 | 57 | -1 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
DRY_X_015 | 2026W06 | 58 | -2 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
TWR_Z_016 | 2026W20 | 72 | 12 | 2026W32 | 2026W32 | 2026-08-10 | 2026W31 | 2026-08-03 |  | 0 | -1 | 정상
TWR_Z_016 | 2026W21 | 73 | 11 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W22 | 74 | 10 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W23 | 75 | 9 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W24 | 76 | 8 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W25 | 77 | 7 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W26 | 78 | 6 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W27 | 79 | 5 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W28 | 80 | 4 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W29 | 81 | 3 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W30 | 82 | 2 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W31 | 83 | 1 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W32 | 84 | 0 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W33 | 85 | -1 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
TWR_Z_016 | 2026W34 | 86 | -2 | 2026W32 | 2026W32 | 2026-08-10 | 2026W32 | 2026-08-10 |  | 0 | 0 | 정상
WASH_F_017 | 2025W44 | 44 | 12 | 2026W04 | 2026W04 | 2026-01-26 | 2026W06 | 2026-02-09 | 2026W07 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_017 | 2025W45 | 45 | 11 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_017 | 2025W46 | 46 | 10 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2025W47 | 47 | 9 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2025W48 | 48 | 8 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_017 | 2025W49 | 49 | 7 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_017 | 2025W50 | 50 | 6 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_017 | 2025W51 | 51 | 5 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2025W52 | 52 | 4 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_017 | 2026W01 | 53 | 3 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2026W02 | 54 | 2 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2026W03 | 55 | 1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2026W04 | 56 | 0 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_017 | 2026W05 | 57 | -1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_017 | 2026W06 | 58 | -2 | 2026W04 | 2026W04 | 2026-01-26 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_017 | 2026W07 | 59 | 0 | 2026W04 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 3 | 0 | 정상
WASH_F_017 | 2026W08 | 60 | -1 | 2026W04 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 3 | 0 | 정상
WASH_F_017 | 2026W09 | 61 | -2 | 2026W04 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 3 | 0 | 정상
WASH_T_018 | 2026W20 | 72 | 12 | 2026W32 | 2026W32 | 2026-08-10 | 2026W37 | 2026-09-14 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W21 | 73 | 11 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_018 | 2026W22 | 74 | 10 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W23 | 75 | 9 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_018 | 2026W24 | 76 | 8 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W25 | 77 | 7 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_018 | 2026W26 | 78 | 6 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W27 | 79 | 5 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_018 | 2026W28 | 80 | 4 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W29 | 81 | 3 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W30 | 82 | 2 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W31 | 83 | 1 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_018 | 2026W32 | 84 | 0 | 2026W32 | 2026W32 | 2026-08-10 | 2026W38 | 2026-09-21 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_018 | 2026W33 | 85 | 5 | 2026W32 | 2026W38 | 2026-09-21 | 2026W38 | 2026-09-21 |  | 6 | 0 | 정상
WASH_T_018 | 2026W34 | 86 | 4 | 2026W32 | 2026W38 | 2026-09-21 | 2026W38 | 2026-09-21 |  | 6 | 0 | 정상
WASH_T_018 | 2026W35 | 87 | 3 | 2026W32 | 2026W38 | 2026-09-21 | 2026W38 | 2026-09-21 |  | 6 | 0 | 정상
WASH_T_018 | 2026W36 | 88 | 2 | 2026W32 | 2026W38 | 2026-09-21 | 2026W38 | 2026-09-21 |  | 6 | 0 | 정상
DRY_X_019 | 2025W42 | 42 | 12 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W03 | 0 | 0 | 정상
DRY_X_019 | 2025W43 | 43 | 11 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W44 | 44 | 10 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W45 | 45 | 9 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W46 | 46 | 8 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W47 | 47 | 7 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W48 | 48 | 6 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W49 | 49 | 5 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W50 | 50 | 4 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W51 | 51 | 3 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2025W52 | 52 | 2 | 2026W02 | 2026W02 | 2026-01-12 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 1 | 정상
DRY_X_019 | 2026W01 | 53 | 2 | 2026W02 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 1 | 0 | 정상
DRY_X_019 | 2026W02 | 54 | 1 | 2026W02 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 1 | 0 | 정상
DRY_X_019 | 2026W03 | 55 | 0 | 2026W02 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 1 | 0 | 정상
DRY_X_019 | 2026W04 | 56 | -1 | 2026W02 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 1 | 0 | 정상
DRY_X_019 | 2026W05 | 57 | -2 | 2026W02 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 1 | 0 | 정상
TWR_Z_020 | 2026W32 | 84 | 12 | 2026W44 | 2026W44 | 2026-11-02 | 2026W48 | 2026-11-30 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_020 | 2026W33 | 85 | 11 | 2026W44 | 2026W44 | 2026-11-02 | 2026W47 | 2026-11-23 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_020 | 2026W34 | 86 | 10 | 2026W44 | 2026W44 | 2026-11-02 | 2026W48 | 2026-11-30 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_020 | 2026W35 | 87 | 9 | 2026W44 | 2026W44 | 2026-11-02 | 2026W48 | 2026-11-30 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_020 | 2026W36 | 88 | 8 | 2026W44 | 2026W44 | 2026-11-02 | 2026W48 | 2026-11-30 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_021 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W39 | 2026-09-28 |  | 0 | -1 | 정상
WASH_F_021 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_021 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_022 | 2025W51 | 51 | 12 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2025W52 | 52 | 11 | 2026W11 | 2026W11 | 2026-03-16 | 2026W10 | 2026-03-09 | 2026W11 | 0 | -1 | 정상
WASH_T_022 | 2026W01 | 53 | 10 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W02 | 54 | 9 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W03 | 55 | 8 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W04 | 56 | 7 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W05 | 57 | 6 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W06 | 58 | 5 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W07 | 59 | 4 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W08 | 60 | 3 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W09 | 61 | 2 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W10 | 62 | 1 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W11 | 63 | 0 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W12 | 64 | -1 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
WASH_T_022 | 2026W13 | 65 | -2 | 2026W11 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 0 | 정상
DRY_X_023 | 2026W07 | 59 | 12 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W23 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_023 | 2026W08 | 60 | 11 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W09 | 61 | 10 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W10 | 62 | 9 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W11 | 63 | 8 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W12 | 64 | 7 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W13 | 65 | 6 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W14 | 66 | 5 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W15 | 67 | 4 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_023 | 2026W16 | 68 | 3 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W17 | 69 | 2 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W18 | 70 | 1 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W19 | 71 | 0 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_023 | 2026W20 | 72 | -1 | 2026W19 | 2026W19 | 2026-05-11 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_023 | 2026W21 | 73 | 2 | 2026W19 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 4 | 0 | 정상
DRY_X_023 | 2026W22 | 74 | 1 | 2026W19 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 4 | 0 | 정상
DRY_X_023 | 2026W23 | 75 | 0 | 2026W19 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 4 | 0 | 정상
DRY_X_023 | 2026W24 | 76 | -1 | 2026W19 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 4 | 0 | 정상
DRY_X_023 | 2026W25 | 77 | -2 | 2026W19 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 4 | 0 | 정상
TWR_Z_024 | 2025W51 | 51 | 12 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2025W52 | 52 | 11 | 2026W11 | 2026W11 | 2026-03-16 | 2026W14 | 2026-04-06 | 2026W15 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W01 | 53 | 10 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W02 | 54 | 9 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W03 | 55 | 8 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W04 | 56 | 7 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_024 | 2026W05 | 57 | 6 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W06 | 58 | 5 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W07 | 59 | 4 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W08 | 60 | 3 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W09 | 61 | 2 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W10 | 62 | 1 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W11 | 63 | 0 | 2026W11 | 2026W11 | 2026-03-16 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_024 | 2026W12 | 64 | 3 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
TWR_Z_024 | 2026W13 | 65 | 2 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
TWR_Z_024 | 2026W14 | 66 | 1 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
TWR_Z_024 | 2026W15 | 67 | 0 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
TWR_Z_024 | 2026W16 | 68 | -1 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
TWR_Z_024 | 2026W17 | 69 | -2 | 2026W11 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 4 | 0 | 정상
WASH_F_025 | 2026W01 | 53 | 12 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_025 | 2026W02 | 54 | 11 | 2026W13 | 2026W13 | 2026-03-30 | 2026W14 | 2026-04-06 | 2026W15 | 0 | 1 | 정상
WASH_F_025 | 2026W03 | 55 | 10 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_025 | 2026W04 | 56 | 9 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_025 | 2026W05 | 57 | 8 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_025 | 2026W06 | 58 | 7 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_025 | 2026W07 | 59 | 6 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_025 | 2026W08 | 60 | 5 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_025 | 2026W09 | 61 | 4 | 2026W13 | 2026W13 | 2026-03-30 | 2026W15 | 2026-04-13 | 2026W15 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_025 | 2026W10 | 62 | 5 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W11 | 63 | 4 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W12 | 64 | 3 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W13 | 65 | 2 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W14 | 66 | 1 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W15 | 67 | 0 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W16 | 68 | -1 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_F_025 | 2026W17 | 69 | -2 | 2026W13 | 2026W15 | 2026-04-13 | 2026W15 | 2026-04-13 | 2026W15 | 2 | 0 | 정상
WASH_T_026 | 2026W23 | 75 | 12 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_026 | 2026W24 | 76 | 11 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_026 | 2026W25 | 77 | 10 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W26 | 78 | 9 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W27 | 79 | 8 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_026 | 2026W28 | 80 | 7 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_026 | 2026W29 | 81 | 6 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_026 | 2026W30 | 82 | 5 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_026 | 2026W31 | 83 | 4 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W32 | 84 | 3 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W33 | 85 | 2 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W34 | 86 | 1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_026 | 2026W35 | 87 | 0 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_026 | 2026W36 | 88 | -1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W38 | 2026-09-21 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_027 | 2025W46 | 46 | 12 | 2026W06 | 2026W06 | 2026-02-09 | 2026W08 | 2026-02-23 | 2026W09 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2025W47 | 47 | 11 | 2026W06 | 2026W06 | 2026-02-09 | 2026W08 | 2026-02-23 | 2026W09 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2025W48 | 48 | 10 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_027 | 2025W49 | 49 | 9 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2025W50 | 50 | 8 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_027 | 2025W51 | 51 | 7 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2025W52 | 52 | 6 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2026W01 | 53 | 5 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2026W02 | 54 | 4 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_027 | 2026W03 | 55 | 3 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2026W04 | 56 | 2 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_027 | 2026W05 | 57 | 1 | 2026W06 | 2026W06 | 2026-02-09 | 2026W09 | 2026-03-02 | 2026W09 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_027 | 2026W06 | 58 | 3 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
DRY_X_027 | 2026W07 | 59 | 2 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
DRY_X_027 | 2026W08 | 60 | 1 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
DRY_X_027 | 2026W09 | 61 | 0 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
DRY_X_027 | 2026W10 | 62 | -1 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
DRY_X_027 | 2026W11 | 63 | -2 | 2026W06 | 2026W09 | 2026-03-02 | 2026W09 | 2026-03-02 | 2026W09 | 3 | 0 | 정상
TWR_Z_028 | 2026W24 | 76 | 12 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W25 | 77 | 11 | 2026W36 | 2026W36 | 2026-09-07 | 2026W35 | 2026-08-31 |  | 0 | -1 | 정상
TWR_Z_028 | 2026W26 | 78 | 10 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W27 | 79 | 9 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W28 | 80 | 8 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W29 | 81 | 7 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W30 | 82 | 6 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W31 | 83 | 5 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W32 | 84 | 4 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W33 | 85 | 3 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W34 | 86 | 2 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W35 | 87 | 1 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_028 | 2026W36 | 88 | 0 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
WASH_F_029 | 2026W26 | 78 | 12 | 2026W38 | 2026W38 | 2026-09-21 | 2026W41 | 2026-10-12 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_029 | 2026W27 | 79 | 11 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_029 | 2026W28 | 80 | 10 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W29 | 81 | 9 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W30 | 82 | 8 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
WASH_F_029 | 2026W31 | 83 | 7 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W32 | 84 | 6 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W33 | 85 | 5 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W34 | 86 | 4 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_029 | 2026W35 | 87 | 3 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_029 | 2026W36 | 88 | 2 | 2026W38 | 2026W38 | 2026-09-21 | 2026W42 | 2026-10-19 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W11 | 63 | 12 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W12 | 64 | 11 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W25 | 0 | 1 | 정상
WASH_T_030 | 2026W13 | 65 | 10 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_030 | 2026W14 | 66 | 9 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W15 | 67 | 8 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_030 | 2026W16 | 68 | 7 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W17 | 69 | 6 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_030 | 2026W18 | 70 | 5 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W19 | 71 | 4 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_030 | 2026W20 | 72 | 3 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W21 | 73 | 2 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W22 | 74 | 1 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_030 | 2026W23 | 75 | 0 | 2026W23 | 2026W23 | 2026-06-08 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_030 | 2026W24 | 76 | 1 | 2026W23 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 2 | 0 | 정상
WASH_T_030 | 2026W25 | 77 | 0 | 2026W23 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 2 | 0 | 정상
WASH_T_030 | 2026W26 | 78 | -1 | 2026W23 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 2 | 0 | 정상
WASH_T_030 | 2026W27 | 79 | -2 | 2026W23 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 2 | 0 | 정상
DRY_X_031 | 2025W43 | 43 | 12 | 2026W03 | 2026W03 | 2026-01-19 | 2026W06 | 2026-02-09 | 2026W07 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_031 | 2025W44 | 44 | 11 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_031 | 2025W45 | 45 | 10 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_031 | 2025W46 | 46 | 9 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_031 | 2025W47 | 47 | 8 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_031 | 2025W48 | 48 | 7 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_031 | 2025W49 | 49 | 6 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_031 | 2025W50 | 50 | 5 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_031 | 2025W51 | 51 | 4 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_031 | 2025W52 | 52 | 3 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_031 | 2026W01 | 53 | 2 | 2026W03 | 2026W03 | 2026-01-19 | 2026W07 | 2026-02-16 | 2026W07 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_031 | 2026W02 | 54 | 5 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W03 | 55 | 4 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W04 | 56 | 3 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W05 | 57 | 2 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W06 | 58 | 1 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W07 | 59 | 0 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W08 | 60 | -1 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
DRY_X_031 | 2026W09 | 61 | -2 | 2026W03 | 2026W07 | 2026-02-16 | 2026W07 | 2026-02-16 | 2026W07 | 4 | 0 | 정상
TWR_Z_032 | 2026W31 | 83 | 12 | 2026W43 | 2026W43 | 2026-10-26 | 2026W44 | 2026-11-02 |  | 0 | 1 | 정상
TWR_Z_032 | 2026W32 | 84 | 11 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_032 | 2026W33 | 85 | 10 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_032 | 2026W34 | 86 | 9 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_032 | 2026W35 | 87 | 8 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_032 | 2026W36 | 88 | 7 | 2026W43 | 2026W43 | 2026-10-26 | 2026W45 | 2026-11-09 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W27 | 79 | 12 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_033 | 2026W28 | 80 | 11 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
WASH_F_033 | 2026W29 | 81 | 10 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W30 | 82 | 9 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W31 | 83 | 8 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W32 | 84 | 7 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W33 | 85 | 6 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W34 | 86 | 5 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_033 | 2026W35 | 87 | 4 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_033 | 2026W36 | 88 | 3 | 2026W39 | 2026W39 | 2026-09-28 | 2026W41 | 2026-10-12 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_034 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_034 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_034 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
DRY_X_035 | 2026W23 | 75 | 12 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_035 | 2026W24 | 76 | 11 | 2026W35 | 2026W35 | 2026-08-31 | 2026W36 | 2026-09-07 |  | 0 | 1 | 정상
DRY_X_035 | 2026W25 | 77 | 10 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_035 | 2026W26 | 78 | 9 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W27 | 79 | 8 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W28 | 80 | 7 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W29 | 81 | 6 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W30 | 82 | 5 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W31 | 83 | 4 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W32 | 84 | 3 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_035 | 2026W33 | 85 | 2 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W34 | 86 | 1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_035 | 2026W35 | 87 | 0 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_035 | 2026W36 | 88 | -1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W37 | 2026-09-14 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_036 | 2025W36 | 36 | 12 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W37 | 37 | 11 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W38 | 38 | 10 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W39 | 39 | 9 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W40 | 40 | 8 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W41 | 41 | 7 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W42 | 42 | 6 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W43 | 43 | 5 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W44 | 44 | 4 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W45 | 45 | 3 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W46 | 46 | 2 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W47 | 47 | 1 | 2025W48 | 2025W48 | 2025-12-01 | 2025W49 | 2025-12-08 | 2025W49 | 0 | 1 | 정상
TWR_Z_036 | 2025W48 | 48 | 1 | 2025W48 | 2025W49 | 2025-12-08 | 2025W49 | 2025-12-08 | 2025W49 | 1 | 0 | 정상
TWR_Z_036 | 2025W49 | 49 | 0 | 2025W48 | 2025W49 | 2025-12-08 | 2025W49 | 2025-12-08 | 2025W49 | 1 | 0 | 정상
TWR_Z_036 | 2025W50 | 50 | -1 | 2025W48 | 2025W49 | 2025-12-08 | 2025W49 | 2025-12-08 | 2025W49 | 1 | 0 | 정상
TWR_Z_036 | 2025W51 | 51 | -2 | 2025W48 | 2025W49 | 2025-12-08 | 2025W49 | 2025-12-08 | 2025W49 | 1 | 0 | 정상
WASH_F_037 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_F_037 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_F_037 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W41 | 2026-10-12 |  | 0 | 1 | 정상
WASH_T_038 | 2025W40 | 40 | 12 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W41 | 41 | 11 | 2025W52 | 2025W52 | 2025-12-29 | 2025W51 | 2025-12-22 | 2025W52 | 0 | -1 | 정상
WASH_T_038 | 2025W42 | 42 | 10 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W43 | 43 | 9 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W44 | 44 | 8 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W45 | 45 | 7 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W46 | 46 | 6 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W47 | 47 | 5 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W48 | 48 | 4 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W49 | 49 | 3 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W50 | 50 | 2 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W51 | 51 | 1 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2025W52 | 52 | 0 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2026W01 | 53 | -1 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
WASH_T_038 | 2026W02 | 54 | -2 | 2025W52 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 0 | 정상
DRY_X_039 | 2026W03 | 55 | 12 | 2026W15 | 2026W15 | 2026-04-13 | 2026W18 | 2026-05-04 | 2026W19 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W04 | 56 | 11 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W05 | 57 | 10 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_039 | 2026W06 | 58 | 9 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_039 | 2026W07 | 59 | 8 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W08 | 60 | 7 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_039 | 2026W09 | 61 | 6 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_039 | 2026W10 | 62 | 5 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_039 | 2026W11 | 63 | 4 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W12 | 64 | 3 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W13 | 65 | 2 | 2026W15 | 2026W15 | 2026-04-13 | 2026W19 | 2026-05-11 | 2026W19 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_039 | 2026W14 | 66 | 5 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W15 | 67 | 4 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W16 | 68 | 3 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W17 | 69 | 2 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W18 | 70 | 1 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W19 | 71 | 0 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W20 | 72 | -1 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
DRY_X_039 | 2026W21 | 73 | -2 | 2026W15 | 2026W19 | 2026-05-11 | 2026W19 | 2026-05-11 | 2026W19 | 4 | 0 | 정상
TWR_Z_040 | 2025W43 | 43 | 12 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W44 | 44 | 11 | 2026W03 | 2026W03 | 2026-01-19 | 2026W02 | 2026-01-12 | 2026W03 | 0 | -1 | 정상
TWR_Z_040 | 2025W45 | 45 | 10 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W46 | 46 | 9 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W47 | 47 | 8 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W48 | 48 | 7 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W49 | 49 | 6 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W50 | 50 | 5 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W51 | 51 | 4 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2025W52 | 52 | 3 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2026W01 | 53 | 2 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2026W02 | 54 | 1 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2026W03 | 55 | 0 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2026W04 | 56 | -1 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
TWR_Z_040 | 2026W05 | 57 | -2 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W03 | 0 | 0 | 정상
WASH_F_041 | 2026W14 | 66 | 12 | 2026W26 | 2026W26 | 2026-06-29 | 2026W25 | 2026-06-22 | 2026W26 | 0 | -1 | 정상
WASH_F_041 | 2026W15 | 67 | 11 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W16 | 68 | 10 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W17 | 69 | 9 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W18 | 70 | 8 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W19 | 71 | 7 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W20 | 72 | 6 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W21 | 73 | 5 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W22 | 74 | 4 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W23 | 75 | 3 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W24 | 76 | 2 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W25 | 77 | 1 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W26 | 78 | 0 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W27 | 79 | -1 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_F_041 | 2026W28 | 80 | -2 | 2026W26 | 2026W26 | 2026-06-29 | 2026W26 | 2026-06-29 | 2026W26 | 0 | 0 | 정상
WASH_T_042 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
WASH_T_042 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 0 | 0 | 정상
DRY_X_043 | 2026W03 | 55 | 12 | 2026W15 | 2026W15 | 2026-04-13 | 2026W16 | 2026-04-20 | 2026W17 | 0 | 1 | 정상
DRY_X_043 | 2026W04 | 56 | 11 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W05 | 57 | 10 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_043 | 2026W06 | 58 | 9 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W07 | 59 | 8 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W08 | 60 | 7 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W09 | 61 | 6 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W10 | 62 | 5 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W11 | 63 | 4 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W12 | 64 | 3 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_043 | 2026W13 | 65 | 2 | 2026W15 | 2026W15 | 2026-04-13 | 2026W17 | 2026-04-27 | 2026W17 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_043 | 2026W14 | 66 | 3 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
DRY_X_043 | 2026W15 | 67 | 2 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
DRY_X_043 | 2026W16 | 68 | 1 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
DRY_X_043 | 2026W17 | 69 | 0 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
DRY_X_043 | 2026W18 | 70 | -1 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
DRY_X_043 | 2026W19 | 71 | -2 | 2026W15 | 2026W17 | 2026-04-27 | 2026W17 | 2026-04-27 | 2026W17 | 2 | 0 | 정상
TWR_Z_044 | 2026W21 | 73 | 12 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W22 | 74 | 11 | 2026W33 | 2026W33 | 2026-08-17 | 2026W32 | 2026-08-10 |  | 0 | -1 | 정상
TWR_Z_044 | 2026W23 | 75 | 10 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W24 | 76 | 9 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W25 | 77 | 8 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W26 | 78 | 7 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W27 | 79 | 6 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W28 | 80 | 5 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W29 | 81 | 4 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W30 | 82 | 3 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W31 | 83 | 2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W32 | 84 | 1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W33 | 85 | 0 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W34 | 86 | -1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
TWR_Z_044 | 2026W35 | 87 | -2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W33 | 2026-08-17 |  | 0 | 0 | 정상
WASH_F_045 | 2025W39 | 39 | 12 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W40 | 40 | 11 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W41 | 41 | 10 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W42 | 42 | 9 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W43 | 43 | 8 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W44 | 44 | 7 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W45 | 45 | 6 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W46 | 46 | 5 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W47 | 47 | 4 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W48 | 48 | 3 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W49 | 49 | 2 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W50 | 50 | 1 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
WASH_F_045 | 2025W51 | 51 | 1 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
WASH_F_045 | 2025W52 | 52 | 0 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
WASH_F_045 | 2026W01 | 53 | -1 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
WASH_F_045 | 2026W02 | 54 | -2 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
WASH_T_046 | 2026W29 | 81 | 12 | 2026W41 | 2026W41 | 2026-10-12 | 2026W42 | 2026-10-19 |  | 0 | 1 | 정상
WASH_T_046 | 2026W30 | 82 | 11 | 2026W41 | 2026W41 | 2026-10-12 | 2026W42 | 2026-10-19 |  | 0 | 1 | 정상
WASH_T_046 | 2026W31 | 83 | 10 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_046 | 2026W32 | 84 | 9 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_046 | 2026W33 | 85 | 8 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_046 | 2026W34 | 86 | 7 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_046 | 2026W35 | 87 | 6 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_046 | 2026W36 | 88 | 5 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_047 | 2026W06 | 58 | 12 | 2026W18 | 2026W18 | 2026-05-04 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 1 | 정상
DRY_X_047 | 2026W07 | 59 | 11 | 2026W18 | 2026W18 | 2026-05-04 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 1 | 정상
DRY_X_047 | 2026W08 | 60 | 10 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_047 | 2026W09 | 61 | 9 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W10 | 62 | 8 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W11 | 63 | 7 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W12 | 64 | 6 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W13 | 65 | 5 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W14 | 66 | 4 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W15 | 67 | 3 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W16 | 68 | 2 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W17 | 69 | 1 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_047 | 2026W18 | 70 | 0 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W19 | 71 | -1 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_047 | 2026W20 | 72 | 0 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_047 | 2026W21 | 73 | -1 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_047 | 2026W22 | 74 | -2 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
TWR_Z_048 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_048 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_048 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_048 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_048 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_048 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_048 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_048 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_048 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W44 | 2026-11-02 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_049 | 2025W52 | 52 | 12 | 2026W12 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W13 | 0 | 0 | 정상
WASH_F_049 | 2026W01 | 53 | 11 | 2026W12 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W13 | 0 | 0 | 정상
WASH_F_049 | 2026W02 | 54 | 10 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W03 | 55 | 9 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W04 | 56 | 8 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W05 | 57 | 7 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W06 | 58 | 6 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W07 | 59 | 5 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W08 | 60 | 4 | 2026W12 | 2026W12 | 2026-03-23 | 2026W13 | 2026-03-30 | 2026W13 | 0 | 1 | 정상
WASH_F_049 | 2026W09 | 61 | 4 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W10 | 62 | 3 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W11 | 63 | 2 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W12 | 64 | 1 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W13 | 65 | 0 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W14 | 66 | -1 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_F_049 | 2026W15 | 67 | -2 | 2026W12 | 2026W13 | 2026-03-30 | 2026W13 | 2026-03-30 | 2026W13 | 1 | 0 | 정상
WASH_T_050 | 2026W21 | 73 | 12 | 2026W33 | 2026W33 | 2026-08-17 | 2026W38 | 2026-09-21 |  | 0 | 5 | 심각 | 양산검증(PV) 지연 요소
WASH_T_050 | 2026W22 | 74 | 11 | 2026W33 | 2026W33 | 2026-08-17 | 2026W38 | 2026-09-21 |  | 0 | 5 | 심각 | 공정/부품 리드타임 지연
WASH_T_050 | 2026W23 | 75 | 10 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W24 | 76 | 9 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_050 | 2026W25 | 77 | 8 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_050 | 2026W26 | 78 | 7 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W27 | 79 | 6 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W28 | 80 | 5 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W29 | 81 | 4 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W30 | 82 | 3 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_050 | 2026W31 | 83 | 2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_050 | 2026W32 | 84 | 1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W33 | 85 | 0 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W34 | 86 | -1 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W35 | 87 | -2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_050 | 2026W36 | 88 | -3 | 2026W33 | 2026W33 | 2026-08-17 | 2026W39 | 2026-09-28 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
DRY_X_051 | 2026W27 | 79 | 12 | 2026W39 | 2026W39 | 2026-09-28 | 2026W39 | 2026-09-28 |  | 0 | 0 | 정상
DRY_X_051 | 2026W28 | 80 | 11 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W29 | 81 | 10 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W30 | 82 | 9 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W31 | 83 | 8 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W32 | 84 | 7 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W33 | 85 | 6 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W34 | 86 | 5 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W35 | 87 | 4 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
DRY_X_051 | 2026W36 | 88 | 3 | 2026W39 | 2026W39 | 2026-09-28 | 2026W40 | 2026-10-05 |  | 0 | 1 | 정상
TWR_Z_052 | 2026W20 | 72 | 12 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_052 | 2026W21 | 73 | 11 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_052 | 2026W22 | 74 | 10 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W23 | 75 | 9 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W24 | 76 | 8 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W25 | 77 | 7 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W26 | 78 | 6 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W27 | 79 | 5 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W28 | 80 | 4 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W29 | 81 | 3 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_052 | 2026W30 | 82 | 2 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_052 | 2026W31 | 83 | 1 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
TWR_Z_052 | 2026W32 | 84 | 0 | 2026W32 | 2026W32 | 2026-08-10 | 2026W34 | 2026-08-24 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_052 | 2026W33 | 85 | 1 | 2026W32 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 2 | 0 | 정상
TWR_Z_052 | 2026W34 | 86 | 0 | 2026W32 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 2 | 0 | 정상
TWR_Z_052 | 2026W35 | 87 | -1 | 2026W32 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 2 | 0 | 정상
TWR_Z_052 | 2026W36 | 88 | -2 | 2026W32 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 2 | 0 | 정상
WASH_F_053 | 2025W43 | 43 | 12 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W04 | 0 | 0 | 정상
WASH_F_053 | 2025W44 | 44 | 11 | 2026W03 | 2026W03 | 2026-01-19 | 2026W03 | 2026-01-19 | 2026W04 | 0 | 0 | 정상
WASH_F_053 | 2025W45 | 45 | 10 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W46 | 46 | 9 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W47 | 47 | 8 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W48 | 48 | 7 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W49 | 49 | 6 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W50 | 50 | 5 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W51 | 51 | 4 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2025W52 | 52 | 3 | 2026W03 | 2026W03 | 2026-01-19 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 1 | 정상
WASH_F_053 | 2026W01 | 53 | 3 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_F_053 | 2026W02 | 54 | 2 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_F_053 | 2026W03 | 55 | 1 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_F_053 | 2026W04 | 56 | 0 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_F_053 | 2026W05 | 57 | -1 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_F_053 | 2026W06 | 58 | -2 | 2026W03 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 1 | 0 | 정상
WASH_T_054 | 2025W44 | 44 | 12 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W45 | 45 | 11 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W46 | 46 | 10 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W47 | 47 | 9 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W48 | 48 | 8 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W49 | 49 | 7 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W50 | 50 | 6 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W51 | 51 | 5 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2025W52 | 52 | 4 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W01 | 53 | 3 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W02 | 54 | 2 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W03 | 55 | 1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W04 | 56 | 0 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W05 | 57 | -1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
WASH_T_054 | 2026W06 | 58 | -2 | 2026W04 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 0 | 정상
DRY_X_055 | 2026W32 | 84 | 12 | 2026W44 | 2026W44 | 2026-11-02 | 2026W47 | 2026-11-23 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_055 | 2026W33 | 85 | 11 | 2026W44 | 2026W44 | 2026-11-02 | 2026W46 | 2026-11-16 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_055 | 2026W34 | 86 | 10 | 2026W44 | 2026W44 | 2026-11-02 | 2026W47 | 2026-11-23 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_055 | 2026W35 | 87 | 9 | 2026W44 | 2026W44 | 2026-11-02 | 2026W47 | 2026-11-23 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_055 | 2026W36 | 88 | 8 | 2026W44 | 2026W44 | 2026-11-02 | 2026W47 | 2026-11-23 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W23 | 75 | 12 | 2026W35 | 2026W35 | 2026-08-31 | 2026W39 | 2026-09-28 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W24 | 76 | 11 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W25 | 77 | 10 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W26 | 78 | 9 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W27 | 79 | 8 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W28 | 80 | 7 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 공정/부품 리드타임 지연
TWR_Z_056 | 2026W29 | 81 | 6 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 공정/부품 리드타임 지연
TWR_Z_056 | 2026W30 | 82 | 5 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W31 | 83 | 4 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W32 | 84 | 3 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W33 | 85 | 2 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_056 | 2026W34 | 86 | 6 | 2026W35 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 5 | 0 | 정상
TWR_Z_056 | 2026W35 | 87 | 5 | 2026W35 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 5 | 0 | 정상
TWR_Z_056 | 2026W36 | 88 | 4 | 2026W35 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 5 | 0 | 정상
WASH_F_057 | 2025W38 | 38 | 12 | 2025W50 | 2025W50 | 2025-12-15 | 2025W49 | 2025-12-08 | 2025W50 | 0 | -1 | 정상
WASH_F_057 | 2025W39 | 39 | 11 | 2025W50 | 2025W50 | 2025-12-15 | 2025W49 | 2025-12-08 | 2025W50 | 0 | -1 | 정상
WASH_F_057 | 2025W40 | 40 | 10 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W41 | 41 | 9 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W42 | 42 | 8 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W43 | 43 | 7 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W44 | 44 | 6 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W45 | 45 | 5 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W46 | 46 | 4 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W47 | 47 | 3 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W48 | 48 | 2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W49 | 49 | 1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W50 | 50 | 0 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W51 | 51 | -1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_F_057 | 2025W52 | 52 | -2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W38 | 38 | 12 | 2025W50 | 2025W50 | 2025-12-15 | 2025W49 | 2025-12-08 | 2025W50 | 0 | -1 | 정상
WASH_T_058 | 2025W39 | 39 | 11 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W40 | 40 | 10 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W41 | 41 | 9 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W42 | 42 | 8 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W43 | 43 | 7 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W44 | 44 | 6 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W45 | 45 | 5 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W46 | 46 | 4 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W47 | 47 | 3 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W48 | 48 | 2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W49 | 49 | 1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W50 | 50 | 0 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W51 | 51 | -1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
WASH_T_058 | 2025W52 | 52 | -2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W50 | 0 | 0 | 정상
DRY_X_059 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_059 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_059 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_059 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_059 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_059 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_059 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_059 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_059 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W43 | 2026-10-26 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_060 | 2026W28 | 80 | 12 | 2026W40 | 2026W40 | 2026-10-05 | 2026W45 | 2026-11-09 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W29 | 81 | 11 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W30 | 82 | 10 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W31 | 83 | 9 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_060 | 2026W32 | 84 | 8 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W33 | 85 | 7 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W34 | 86 | 6 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_060 | 2026W35 | 87 | 5 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_060 | 2026W36 | 88 | 4 | 2026W40 | 2026W40 | 2026-10-05 | 2026W46 | 2026-11-16 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W29 | 81 | 12 | 2026W41 | 2026W41 | 2026-10-12 | 2026W42 | 2026-10-19 |  | 0 | 1 | 정상
WASH_F_061 | 2026W30 | 82 | 11 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W31 | 83 | 10 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W32 | 84 | 9 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W33 | 85 | 8 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W34 | 86 | 7 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_061 | 2026W35 | 87 | 6 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_061 | 2026W36 | 88 | 5 | 2026W41 | 2026W41 | 2026-10-12 | 2026W43 | 2026-10-26 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_062 | 2026W11 | 63 | 12 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W24 | 0 | 0 | 정상
WASH_T_062 | 2026W12 | 64 | 11 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W13 | 65 | 10 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W14 | 66 | 9 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W15 | 67 | 8 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W16 | 68 | 7 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W17 | 69 | 6 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W18 | 70 | 5 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W19 | 71 | 4 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W20 | 72 | 3 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W21 | 73 | 2 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_062 | 2026W22 | 74 | 2 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_062 | 2026W23 | 75 | 1 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_062 | 2026W24 | 76 | 0 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_062 | 2026W25 | 77 | -1 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_062 | 2026W26 | 78 | -2 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
DRY_X_063 | 2025W44 | 44 | 12 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W45 | 45 | 11 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W46 | 46 | 10 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W47 | 47 | 9 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W48 | 48 | 8 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W49 | 49 | 7 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_063 | 2025W50 | 50 | 6 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W51 | 51 | 5 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2025W52 | 52 | 4 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2026W01 | 53 | 3 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2026W02 | 54 | 2 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_063 | 2026W03 | 55 | 1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2026W04 | 56 | 0 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_063 | 2026W05 | 57 | -1 | 2026W04 | 2026W04 | 2026-01-26 | 2026W08 | 2026-02-23 | 2026W08 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_063 | 2026W06 | 58 | 2 | 2026W04 | 2026W08 | 2026-02-23 | 2026W08 | 2026-02-23 | 2026W08 | 4 | 0 | 정상
DRY_X_063 | 2026W07 | 59 | 1 | 2026W04 | 2026W08 | 2026-02-23 | 2026W08 | 2026-02-23 | 2026W08 | 4 | 0 | 정상
DRY_X_063 | 2026W08 | 60 | 0 | 2026W04 | 2026W08 | 2026-02-23 | 2026W08 | 2026-02-23 | 2026W08 | 4 | 0 | 정상
DRY_X_063 | 2026W09 | 61 | -1 | 2026W04 | 2026W08 | 2026-02-23 | 2026W08 | 2026-02-23 | 2026W08 | 4 | 0 | 정상
DRY_X_063 | 2026W10 | 62 | -2 | 2026W04 | 2026W08 | 2026-02-23 | 2026W08 | 2026-02-23 | 2026W08 | 4 | 0 | 정상
TWR_Z_064 | 2025W39 | 39 | 12 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W40 | 40 | 11 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W41 | 41 | 10 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W42 | 42 | 9 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W43 | 43 | 8 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W44 | 44 | 7 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W45 | 45 | 6 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W46 | 46 | 5 | 2025W51 | 2025W51 | 2025-12-22 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 1 | 정상
TWR_Z_064 | 2025W47 | 47 | 5 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2025W48 | 48 | 4 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2025W49 | 49 | 3 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2025W50 | 50 | 2 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2025W51 | 51 | 1 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2025W52 | 52 | 0 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2026W01 | 53 | -1 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
TWR_Z_064 | 2026W02 | 54 | -2 | 2025W51 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 1 | 0 | 정상
WASH_F_065 | 2025W42 | 42 | 12 | 2026W02 | 2026W02 | 2026-01-12 | 2026W01 | 2026-01-05 | 2026W02 | 0 | -1 | 정상
WASH_F_065 | 2025W43 | 43 | 11 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W44 | 44 | 10 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W45 | 45 | 9 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W46 | 46 | 8 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W47 | 47 | 7 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W48 | 48 | 6 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W49 | 49 | 5 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W50 | 50 | 4 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W51 | 51 | 3 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2025W52 | 52 | 2 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2026W01 | 53 | 1 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2026W02 | 54 | 0 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2026W03 | 55 | -1 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_F_065 | 2026W04 | 56 | -2 | 2026W02 | 2026W02 | 2026-01-12 | 2026W02 | 2026-01-12 | 2026W02 | 0 | 0 | 정상
WASH_T_066 | 2026W30 | 82 | 12 | 2026W42 | 2026W42 | 2026-10-19 | 2026W47 | 2026-11-23 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
WASH_T_066 | 2026W31 | 83 | 11 | 2026W42 | 2026W42 | 2026-10-19 | 2026W47 | 2026-11-23 |  | 0 | 5 | 심각 | 공정/부품 리드타임 지연
WASH_T_066 | 2026W32 | 84 | 10 | 2026W42 | 2026W42 | 2026-10-19 | 2026W48 | 2026-11-30 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_T_066 | 2026W33 | 85 | 9 | 2026W42 | 2026W42 | 2026-10-19 | 2026W48 | 2026-11-30 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_066 | 2026W34 | 86 | 8 | 2026W42 | 2026W42 | 2026-10-19 | 2026W48 | 2026-11-30 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
WASH_T_066 | 2026W35 | 87 | 7 | 2026W42 | 2026W42 | 2026-10-19 | 2026W48 | 2026-11-30 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
WASH_T_066 | 2026W36 | 88 | 6 | 2026W42 | 2026W42 | 2026-10-19 | 2026W48 | 2026-11-30 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W37 | 37 | 12 | 2025W49 | 2025W49 | 2025-12-08 | 2025W51 | 2025-12-22 | 2025W52 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_067 | 2025W38 | 38 | 11 | 2025W49 | 2025W49 | 2025-12-08 | 2025W51 | 2025-12-22 | 2025W52 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W39 | 39 | 10 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W40 | 40 | 9 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W41 | 41 | 8 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W42 | 42 | 7 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W43 | 43 | 6 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W44 | 44 | 5 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_067 | 2025W45 | 45 | 4 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_067 | 2025W46 | 46 | 3 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W47 | 47 | 2 | 2025W49 | 2025W49 | 2025-12-08 | 2025W52 | 2025-12-29 | 2025W52 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_067 | 2025W48 | 48 | 4 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2025W49 | 49 | 3 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2025W50 | 50 | 2 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2025W51 | 51 | 1 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2025W52 | 52 | 0 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2026W01 | 53 | -1 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
DRY_X_067 | 2026W02 | 54 | -2 | 2025W49 | 2025W52 | 2025-12-29 | 2025W52 | 2025-12-29 | 2025W52 | 3 | 0 | 정상
TWR_Z_068 | 2026W25 | 77 | 12 | 2026W37 | 2026W37 | 2026-09-14 | 2026W39 | 2026-09-28 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W26 | 78 | 11 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
TWR_Z_068 | 2026W27 | 79 | 10 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W28 | 80 | 9 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W29 | 81 | 8 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_068 | 2026W30 | 82 | 7 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_068 | 2026W31 | 83 | 6 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W32 | 84 | 5 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W33 | 85 | 4 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W34 | 86 | 3 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_068 | 2026W35 | 87 | 2 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
TWR_Z_068 | 2026W36 | 88 | 1 | 2026W37 | 2026W37 | 2026-09-14 | 2026W40 | 2026-10-05 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_069 | 2025W38 | 38 | 12 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W51 | 0 | 0 | 정상
WASH_F_069 | 2025W39 | 39 | 11 | 2025W50 | 2025W50 | 2025-12-15 | 2025W50 | 2025-12-15 | 2025W51 | 0 | 0 | 정상
WASH_F_069 | 2025W40 | 40 | 10 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W41 | 41 | 9 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W42 | 42 | 8 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W43 | 43 | 7 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W44 | 44 | 6 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W45 | 45 | 5 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W46 | 46 | 4 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W47 | 47 | 3 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W48 | 48 | 2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W49 | 49 | 1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W50 | 50 | 0 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
WASH_F_069 | 2025W51 | 51 | 0 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
WASH_F_069 | 2025W52 | 52 | -1 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
WASH_F_069 | 2026W01 | 53 | -2 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
WASH_T_070 | 2026W11 | 63 | 12 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W12 | 64 | 11 | 2026W23 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W24 | 0 | 0 | 정상
WASH_T_070 | 2026W13 | 65 | 10 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W14 | 66 | 9 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W15 | 67 | 8 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W16 | 68 | 7 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W17 | 69 | 6 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W18 | 70 | 5 | 2026W23 | 2026W23 | 2026-06-08 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 1 | 정상
WASH_T_070 | 2026W19 | 71 | 5 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W20 | 72 | 4 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W21 | 73 | 3 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W22 | 74 | 2 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W23 | 75 | 1 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W24 | 76 | 0 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W25 | 77 | -1 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
WASH_T_070 | 2026W26 | 78 | -2 | 2026W23 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 1 | 0 | 정상
DRY_X_071 | 2025W38 | 38 | 12 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W39 | 39 | 11 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W40 | 40 | 10 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W41 | 41 | 9 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W42 | 42 | 8 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W43 | 43 | 7 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W44 | 44 | 6 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W45 | 45 | 5 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W46 | 46 | 4 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W47 | 47 | 3 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W48 | 48 | 2 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W49 | 49 | 1 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W50 | 50 | 0 | 2025W50 | 2025W50 | 2025-12-15 | 2025W51 | 2025-12-22 | 2025W51 | 0 | 1 | 정상
DRY_X_071 | 2025W51 | 51 | 0 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
DRY_X_071 | 2025W52 | 52 | -1 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
DRY_X_071 | 2026W01 | 53 | -2 | 2025W50 | 2025W51 | 2025-12-22 | 2025W51 | 2025-12-22 | 2025W51 | 1 | 0 | 정상
TWR_Z_072 | 2026W24 | 76 | 12 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_072 | 2026W25 | 77 | 11 | 2026W36 | 2026W36 | 2026-09-07 | 2026W36 | 2026-09-07 |  | 0 | 0 | 정상
TWR_Z_072 | 2026W26 | 78 | 10 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W27 | 79 | 9 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W28 | 80 | 8 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W29 | 81 | 7 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W30 | 82 | 6 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W31 | 83 | 5 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W32 | 84 | 4 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W33 | 85 | 3 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W34 | 86 | 2 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W35 | 87 | 1 | 2026W36 | 2026W36 | 2026-09-07 | 2026W37 | 2026-09-14 |  | 0 | 1 | 정상
TWR_Z_072 | 2026W36 | 88 | 1 | 2026W36 | 2026W37 | 2026-09-14 | 2026W37 | 2026-09-14 |  | 1 | 0 | 정상
WASH_F_073 | 2025W48 | 48 | 12 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2025W49 | 49 | 11 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2025W50 | 50 | 10 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2025W51 | 51 | 9 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2025W52 | 52 | 8 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2026W01 | 53 | 7 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2026W02 | 54 | 6 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_073 | 2026W03 | 55 | 5 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_073 | 2026W04 | 56 | 4 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2026W05 | 57 | 3 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2026W06 | 58 | 2 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_073 | 2026W07 | 59 | 1 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_F_073 | 2026W08 | 60 | 0 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_073 | 2026W09 | 61 | -1 | 2026W08 | 2026W08 | 2026-02-23 | 2026W10 | 2026-03-09 | 2026W10 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_F_073 | 2026W10 | 62 | 0 | 2026W08 | 2026W10 | 2026-03-09 | 2026W10 | 2026-03-09 | 2026W10 | 2 | 0 | 정상
WASH_F_073 | 2026W11 | 63 | -1 | 2026W08 | 2026W10 | 2026-03-09 | 2026W10 | 2026-03-09 | 2026W10 | 2 | 0 | 정상
WASH_F_073 | 2026W12 | 64 | -2 | 2026W08 | 2026W10 | 2026-03-09 | 2026W10 | 2026-03-09 | 2026W10 | 2 | 0 | 정상
WASH_T_074 | 2026W12 | 64 | 12 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W25 | 0 | 0 | 정상
WASH_T_074 | 2026W13 | 65 | 11 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W14 | 66 | 10 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W15 | 67 | 9 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W16 | 68 | 8 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W17 | 69 | 7 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W18 | 70 | 6 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W19 | 71 | 5 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W20 | 72 | 4 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W21 | 73 | 3 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W22 | 74 | 2 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W23 | 75 | 1 | 2026W24 | 2026W24 | 2026-06-15 | 2026W25 | 2026-06-22 | 2026W25 | 0 | 1 | 정상
WASH_T_074 | 2026W24 | 76 | 1 | 2026W24 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 1 | 0 | 정상
WASH_T_074 | 2026W25 | 77 | 0 | 2026W24 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 1 | 0 | 정상
WASH_T_074 | 2026W26 | 78 | -1 | 2026W24 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 1 | 0 | 정상
WASH_T_074 | 2026W27 | 79 | -2 | 2026W24 | 2026W25 | 2026-06-22 | 2026W25 | 2026-06-22 | 2026W25 | 1 | 0 | 정상
DRY_X_075 | 2026W10 | 62 | 12 | 2026W22 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W23 | 0 | 0 | 정상
DRY_X_075 | 2026W11 | 63 | 11 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W12 | 64 | 10 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W13 | 65 | 9 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W14 | 66 | 8 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W15 | 67 | 7 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W16 | 68 | 6 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W17 | 69 | 5 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W18 | 70 | 4 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W19 | 71 | 3 | 2026W22 | 2026W22 | 2026-06-01 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 1 | 정상
DRY_X_075 | 2026W20 | 72 | 3 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
DRY_X_075 | 2026W21 | 73 | 2 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
DRY_X_075 | 2026W22 | 74 | 1 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
DRY_X_075 | 2026W23 | 75 | 0 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
DRY_X_075 | 2026W24 | 76 | -1 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
DRY_X_075 | 2026W25 | 77 | -2 | 2026W22 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 1 | 0 | 정상
TWR_Z_076 | 2026W08 | 60 | 12 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W09 | 61 | 11 | 2026W20 | 2026W20 | 2026-05-18 | 2026W19 | 2026-05-11 | 2026W20 | 0 | -1 | 정상
TWR_Z_076 | 2026W10 | 62 | 10 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W11 | 63 | 9 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W12 | 64 | 8 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W13 | 65 | 7 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W14 | 66 | 6 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W15 | 67 | 5 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W16 | 68 | 4 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W17 | 69 | 3 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W18 | 70 | 2 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W19 | 71 | 1 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W20 | 72 | 0 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W21 | 73 | -1 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
TWR_Z_076 | 2026W22 | 74 | -2 | 2026W20 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 0 | 정상
WASH_F_077 | 2026W29 | 81 | 12 | 2026W41 | 2026W41 | 2026-10-12 | 2026W44 | 2026-11-02 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_077 | 2026W30 | 82 | 11 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_077 | 2026W31 | 83 | 10 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_077 | 2026W32 | 84 | 9 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_077 | 2026W33 | 85 | 8 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_F_077 | 2026W34 | 86 | 7 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_077 | 2026W35 | 87 | 6 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_F_077 | 2026W36 | 88 | 5 | 2026W41 | 2026W41 | 2026-10-12 | 2026W45 | 2026-11-09 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
WASH_T_078 | 2026W04 | 56 | 12 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W05 | 57 | 11 | 2026W16 | 2026W16 | 2026-04-20 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W06 | 58 | 10 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W07 | 59 | 9 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W08 | 60 | 8 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
WASH_T_078 | 2026W09 | 61 | 7 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_078 | 2026W10 | 62 | 6 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_078 | 2026W11 | 63 | 5 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W12 | 64 | 4 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W13 | 65 | 3 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W14 | 66 | 2 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W15 | 67 | 1 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_078 | 2026W16 | 68 | 4 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W17 | 69 | 3 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W18 | 70 | 2 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W19 | 71 | 1 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W20 | 72 | 0 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W21 | 73 | -1 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
WASH_T_078 | 2026W22 | 74 | -2 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
DRY_X_079 | 2026W07 | 59 | 12 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_079 | 2026W08 | 60 | 11 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W09 | 61 | 10 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W10 | 62 | 9 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W11 | 63 | 8 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W12 | 64 | 7 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W13 | 65 | 6 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W14 | 66 | 5 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
DRY_X_079 | 2026W15 | 67 | 4 | 2026W19 | 2026W19 | 2026-05-11 | 2026W22 | 2026-06-01 | 2026W22 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_079 | 2026W16 | 68 | 6 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W17 | 69 | 5 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W18 | 70 | 4 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W19 | 71 | 3 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W20 | 72 | 2 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W21 | 73 | 1 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W22 | 74 | 0 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W23 | 75 | -1 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
DRY_X_079 | 2026W24 | 76 | -2 | 2026W19 | 2026W22 | 2026-06-01 | 2026W22 | 2026-06-01 | 2026W22 | 3 | 0 | 정상
TWR_Z_080 | 2026W32 | 84 | 12 | 2026W44 | 2026W44 | 2026-11-02 | 2026W43 | 2026-10-26 |  | 0 | -1 | 정상
TWR_Z_080 | 2026W33 | 85 | 11 | 2026W44 | 2026W44 | 2026-11-02 | 2026W44 | 2026-11-02 |  | 0 | 0 | 정상
TWR_Z_080 | 2026W34 | 86 | 10 | 2026W44 | 2026W44 | 2026-11-02 | 2026W44 | 2026-11-02 |  | 0 | 0 | 정상
TWR_Z_080 | 2026W35 | 87 | 9 | 2026W44 | 2026W44 | 2026-11-02 | 2026W44 | 2026-11-02 |  | 0 | 0 | 정상
TWR_Z_080 | 2026W36 | 88 | 8 | 2026W44 | 2026W44 | 2026-11-02 | 2026W44 | 2026-11-02 |  | 0 | 0 | 정상
WASH_F_081 | 2025W41 | 41 | 12 | 2026W01 | 2026W01 | 2026-01-05 | 2026W03 | 2026-01-19 | 2026W04 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W42 | 42 | 11 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W43 | 43 | 10 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_081 | 2025W44 | 44 | 9 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W45 | 45 | 8 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_081 | 2025W46 | 46 | 7 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_081 | 2025W47 | 47 | 6 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W48 | 48 | 5 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W49 | 49 | 4 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W50 | 50 | 3 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W51 | 51 | 2 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2025W52 | 52 | 1 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_081 | 2026W01 | 53 | 0 | 2026W01 | 2026W01 | 2026-01-05 | 2026W04 | 2026-01-26 | 2026W04 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_081 | 2026W02 | 54 | 2 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
WASH_F_081 | 2026W03 | 55 | 1 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
WASH_F_081 | 2026W04 | 56 | 0 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
WASH_F_081 | 2026W05 | 57 | -1 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
WASH_F_081 | 2026W06 | 58 | -2 | 2026W01 | 2026W04 | 2026-01-26 | 2026W04 | 2026-01-26 | 2026W04 | 3 | 0 | 정상
WASH_T_082 | 2026W32 | 84 | 12 | 2026W44 | 2026W44 | 2026-11-02 | 2026W45 | 2026-11-09 |  | 0 | 1 | 정상
WASH_T_082 | 2026W33 | 85 | 11 | 2026W44 | 2026W44 | 2026-11-02 | 2026W46 | 2026-11-16 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_082 | 2026W34 | 86 | 10 | 2026W44 | 2026W44 | 2026-11-02 | 2026W46 | 2026-11-16 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_082 | 2026W35 | 87 | 9 | 2026W44 | 2026W44 | 2026-11-02 | 2026W46 | 2026-11-16 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_082 | 2026W36 | 88 | 8 | 2026W44 | 2026W44 | 2026-11-02 | 2026W46 | 2026-11-16 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_083 | 2026W06 | 58 | 12 | 2026W18 | 2026W18 | 2026-05-04 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 1 | 정상
DRY_X_083 | 2026W07 | 59 | 11 | 2026W18 | 2026W18 | 2026-05-04 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 1 | 정상
DRY_X_083 | 2026W08 | 60 | 10 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_083 | 2026W09 | 61 | 9 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
DRY_X_083 | 2026W10 | 62 | 8 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_083 | 2026W11 | 63 | 7 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_083 | 2026W12 | 64 | 6 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_083 | 2026W13 | 65 | 5 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
DRY_X_083 | 2026W14 | 66 | 4 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_083 | 2026W15 | 67 | 3 | 2026W18 | 2026W18 | 2026-05-04 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
DRY_X_083 | 2026W16 | 68 | 4 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W17 | 69 | 3 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W18 | 70 | 2 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W19 | 71 | 1 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W20 | 72 | 0 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W21 | 73 | -1 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
DRY_X_083 | 2026W22 | 74 | -2 | 2026W18 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 2 | 0 | 정상
TWR_Z_084 | 2025W48 | 48 | 12 | 2026W08 | 2026W08 | 2026-02-23 | 2026W11 | 2026-03-16 | 2026W12 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
TWR_Z_084 | 2025W49 | 49 | 11 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_084 | 2025W50 | 50 | 10 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_084 | 2025W51 | 51 | 9 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_084 | 2025W52 | 52 | 8 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_084 | 2026W01 | 53 | 7 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_084 | 2026W02 | 54 | 6 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
TWR_Z_084 | 2026W03 | 55 | 5 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_084 | 2026W04 | 56 | 4 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_084 | 2026W05 | 57 | 3 | 2026W08 | 2026W08 | 2026-02-23 | 2026W12 | 2026-03-23 | 2026W12 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_084 | 2026W06 | 58 | 6 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W07 | 59 | 5 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W08 | 60 | 4 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W09 | 61 | 3 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W10 | 62 | 2 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W11 | 63 | 1 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W12 | 64 | 0 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W13 | 65 | -1 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
TWR_Z_084 | 2026W14 | 66 | -2 | 2026W08 | 2026W12 | 2026-03-23 | 2026W12 | 2026-03-23 | 2026W12 | 4 | 0 | 정상
WASH_F_085 | 2026W22 | 74 | 12 | 2026W34 | 2026W34 | 2026-08-24 | 2026W36 | 2026-09-07 |  | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W23 | 75 | 11 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_085 | 2026W24 | 76 | 10 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W25 | 77 | 9 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_085 | 2026W26 | 78 | 8 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W27 | 79 | 7 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W28 | 80 | 6 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W29 | 81 | 5 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_085 | 2026W30 | 82 | 4 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_085 | 2026W31 | 83 | 3 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_085 | 2026W32 | 84 | 2 | 2026W34 | 2026W34 | 2026-08-24 | 2026W37 | 2026-09-14 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_085 | 2026W33 | 85 | 4 | 2026W34 | 2026W37 | 2026-09-14 | 2026W37 | 2026-09-14 |  | 3 | 0 | 정상
WASH_F_085 | 2026W34 | 86 | 3 | 2026W34 | 2026W37 | 2026-09-14 | 2026W37 | 2026-09-14 |  | 3 | 0 | 정상
WASH_F_085 | 2026W35 | 87 | 2 | 2026W34 | 2026W37 | 2026-09-14 | 2026W37 | 2026-09-14 |  | 3 | 0 | 정상
WASH_F_085 | 2026W36 | 88 | 1 | 2026W34 | 2026W37 | 2026-09-14 | 2026W37 | 2026-09-14 |  | 3 | 0 | 정상
WASH_T_086 | 2026W05 | 57 | 12 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_086 | 2026W06 | 58 | 11 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W07 | 59 | 10 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W08 | 60 | 9 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_086 | 2026W09 | 61 | 8 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W10 | 62 | 7 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_086 | 2026W11 | 63 | 6 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_086 | 2026W12 | 64 | 5 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_086 | 2026W13 | 65 | 4 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W14 | 66 | 3 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_086 | 2026W15 | 67 | 2 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_T_086 | 2026W16 | 68 | 1 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W17 | 69 | 0 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_086 | 2026W18 | 70 | -1 | 2026W17 | 2026W17 | 2026-04-27 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_T_086 | 2026W19 | 71 | 1 | 2026W17 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 3 | 0 | 정상
WASH_T_086 | 2026W20 | 72 | 0 | 2026W17 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 3 | 0 | 정상
WASH_T_086 | 2026W21 | 73 | -1 | 2026W17 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 3 | 0 | 정상
WASH_T_086 | 2026W22 | 74 | -2 | 2026W17 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 3 | 0 | 정상
DRY_X_087 | 2026W04 | 56 | 12 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W05 | 57 | 11 | 2026W16 | 2026W16 | 2026-04-20 | 2026W19 | 2026-05-11 | 2026W20 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
DRY_X_087 | 2026W06 | 58 | 10 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W07 | 59 | 9 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W08 | 60 | 8 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W09 | 61 | 7 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W10 | 62 | 6 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_087 | 2026W11 | 63 | 5 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W12 | 64 | 4 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W13 | 65 | 3 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_087 | 2026W14 | 66 | 2 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W15 | 67 | 1 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W16 | 68 | 0 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_087 | 2026W17 | 69 | -1 | 2026W16 | 2026W16 | 2026-04-20 | 2026W20 | 2026-05-18 | 2026W20 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_087 | 2026W18 | 70 | 2 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
DRY_X_087 | 2026W19 | 71 | 1 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
DRY_X_087 | 2026W20 | 72 | 0 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
DRY_X_087 | 2026W21 | 73 | -1 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
DRY_X_087 | 2026W22 | 74 | -2 | 2026W16 | 2026W20 | 2026-05-18 | 2026W20 | 2026-05-18 | 2026W20 | 4 | 0 | 정상
TWR_Z_088 | 2026W14 | 66 | 12 | 2026W26 | 2026W26 | 2026-06-29 | 2026W29 | 2026-07-20 | 2026W30 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W15 | 67 | 11 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W16 | 68 | 10 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W17 | 69 | 9 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_088 | 2026W18 | 70 | 8 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W19 | 71 | 7 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_088 | 2026W20 | 72 | 6 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W21 | 73 | 5 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_088 | 2026W22 | 74 | 4 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_088 | 2026W23 | 75 | 3 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W24 | 76 | 2 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W25 | 77 | 1 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_088 | 2026W26 | 78 | 0 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W27 | 79 | -1 | 2026W26 | 2026W26 | 2026-06-29 | 2026W30 | 2026-07-27 | 2026W30 | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_088 | 2026W28 | 80 | 2 | 2026W26 | 2026W30 | 2026-07-27 | 2026W30 | 2026-07-27 | 2026W30 | 4 | 0 | 정상
TWR_Z_088 | 2026W29 | 81 | 1 | 2026W26 | 2026W30 | 2026-07-27 | 2026W30 | 2026-07-27 | 2026W30 | 4 | 0 | 정상
TWR_Z_088 | 2026W30 | 82 | 0 | 2026W26 | 2026W30 | 2026-07-27 | 2026W30 | 2026-07-27 | 2026W30 | 4 | 0 | 정상
TWR_Z_088 | 2026W31 | 83 | -1 | 2026W26 | 2026W30 | 2026-07-27 | 2026W30 | 2026-07-27 | 2026W30 | 4 | 0 | 정상
TWR_Z_088 | 2026W32 | 84 | -2 | 2026W26 | 2026W30 | 2026-07-27 | 2026W30 | 2026-07-27 | 2026W30 | 4 | 0 | 정상
WASH_F_089 | 2026W08 | 60 | 12 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_089 | 2026W09 | 61 | 11 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W10 | 62 | 10 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W11 | 63 | 9 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_089 | 2026W12 | 64 | 8 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W13 | 65 | 7 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_089 | 2026W14 | 66 | 6 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_089 | 2026W15 | 67 | 5 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W16 | 68 | 4 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 양산검증(PV) 지연 요소
WASH_F_089 | 2026W17 | 69 | 3 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W18 | 70 | 2 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W19 | 71 | 1 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 공정/부품 리드타임 지연
WASH_F_089 | 2026W20 | 72 | 0 | 2026W20 | 2026W20 | 2026-05-18 | 2026W23 | 2026-06-08 | 2026W23 | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_F_089 | 2026W21 | 73 | 2 | 2026W20 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 3 | 0 | 정상
WASH_F_089 | 2026W22 | 74 | 1 | 2026W20 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 3 | 0 | 정상
WASH_F_089 | 2026W23 | 75 | 0 | 2026W20 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 3 | 0 | 정상
WASH_F_089 | 2026W24 | 76 | -1 | 2026W20 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 3 | 0 | 정상
WASH_F_089 | 2026W25 | 77 | -2 | 2026W20 | 2026W23 | 2026-06-08 | 2026W23 | 2026-06-08 | 2026W23 | 3 | 0 | 정상
WASH_T_090 | 2026W24 | 76 | 12 | 2026W36 | 2026W36 | 2026-09-07 | 2026W39 | 2026-09-28 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W25 | 77 | 11 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_090 | 2026W26 | 78 | 10 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
WASH_T_090 | 2026W27 | 79 | 9 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W28 | 80 | 8 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W29 | 81 | 7 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W30 | 82 | 6 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
WASH_T_090 | 2026W31 | 83 | 5 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W32 | 84 | 4 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W33 | 85 | 3 | 2026W36 | 2026W36 | 2026-09-07 | 2026W40 | 2026-10-05 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
WASH_T_090 | 2026W34 | 86 | 6 | 2026W36 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 4 | 0 | 정상
WASH_T_090 | 2026W35 | 87 | 5 | 2026W36 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 4 | 0 | 정상
WASH_T_090 | 2026W36 | 88 | 4 | 2026W36 | 2026W40 | 2026-10-05 | 2026W40 | 2026-10-05 |  | 4 | 0 | 정상
DRY_X_091 | 2026W30 | 82 | 12 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_091 | 2026W31 | 83 | 11 | 2026W42 | 2026W42 | 2026-10-19 | 2026W45 | 2026-11-09 |  | 0 | 3 | 주의 | 개발검증(DV) 지연 요소
DRY_X_091 | 2026W32 | 84 | 10 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 공정/부품 리드타임 지연
DRY_X_091 | 2026W33 | 85 | 9 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_091 | 2026W34 | 86 | 8 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
DRY_X_091 | 2026W35 | 87 | 7 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 양산검증(PV) 지연 요소
DRY_X_091 | 2026W36 | 88 | 6 | 2026W42 | 2026W42 | 2026-10-19 | 2026W46 | 2026-11-16 |  | 0 | 4 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W25 | 77 | 12 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W26 | 78 | 11 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W27 | 79 | 10 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W28 | 80 | 9 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_092 | 2026W29 | 81 | 8 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W30 | 82 | 7 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_092 | 2026W31 | 83 | 6 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_092 | 2026W32 | 84 | 5 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W33 | 85 | 4 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W34 | 86 | 3 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_092 | 2026W35 | 87 | 2 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_092 | 2026W36 | 88 | 1 | 2026W37 | 2026W37 | 2026-09-14 | 2026W43 | 2026-10-26 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_F_093 | 2026W12 | 64 | 12 | 2026W24 | 2026W24 | 2026-06-15 | 2026W23 | 2026-06-08 | 2026W24 | 0 | -1 | 정상
WASH_F_093 | 2026W13 | 65 | 11 | 2026W24 | 2026W24 | 2026-06-15 | 2026W23 | 2026-06-08 | 2026W24 | 0 | -1 | 정상
WASH_F_093 | 2026W14 | 66 | 10 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W15 | 67 | 9 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W16 | 68 | 8 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W17 | 69 | 7 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W18 | 70 | 6 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W19 | 71 | 5 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W20 | 72 | 4 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W21 | 73 | 3 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W22 | 74 | 2 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W23 | 75 | 1 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W24 | 76 | 0 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W25 | 77 | -1 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_F_093 | 2026W26 | 78 | -2 | 2026W24 | 2026W24 | 2026-06-15 | 2026W24 | 2026-06-15 | 2026W24 | 0 | 0 | 정상
WASH_T_094 | 2025W50 | 50 | 12 | 2026W10 | 2026W10 | 2026-03-09 | 2026W10 | 2026-03-09 | 2026W11 | 0 | 0 | 정상
WASH_T_094 | 2025W51 | 51 | 11 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2025W52 | 52 | 10 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2026W01 | 53 | 9 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2026W02 | 54 | 8 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2026W03 | 55 | 7 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2026W04 | 56 | 6 | 2026W10 | 2026W10 | 2026-03-09 | 2026W11 | 2026-03-16 | 2026W11 | 0 | 1 | 정상
WASH_T_094 | 2026W05 | 57 | 6 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W06 | 58 | 5 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W07 | 59 | 4 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W08 | 60 | 3 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W09 | 61 | 2 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W10 | 62 | 1 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W11 | 63 | 0 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W12 | 64 | -1 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
WASH_T_094 | 2026W13 | 65 | -2 | 2026W10 | 2026W11 | 2026-03-16 | 2026W11 | 2026-03-16 | 2026W11 | 1 | 0 | 정상
DRY_X_095 | 2026W21 | 73 | 12 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W22 | 74 | 11 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W23 | 75 | 10 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W24 | 76 | 9 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W25 | 77 | 8 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W26 | 78 | 7 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W27 | 79 | 6 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W28 | 80 | 5 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W29 | 81 | 4 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W30 | 82 | 3 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W31 | 83 | 2 | 2026W33 | 2026W33 | 2026-08-17 | 2026W34 | 2026-08-24 |  | 0 | 1 | 정상
DRY_X_095 | 2026W32 | 84 | 2 | 2026W33 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 1 | 0 | 정상
DRY_X_095 | 2026W33 | 85 | 1 | 2026W33 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 1 | 0 | 정상
DRY_X_095 | 2026W34 | 86 | 0 | 2026W33 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 1 | 0 | 정상
DRY_X_095 | 2026W35 | 87 | -1 | 2026W33 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 1 | 0 | 정상
DRY_X_095 | 2026W36 | 88 | -2 | 2026W33 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 1 | 0 | 정상
TWR_Z_096 | 2026W23 | 75 | 12 | 2026W35 | 2026W35 | 2026-08-31 | 2026W40 | 2026-10-05 |  | 0 | 5 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W24 | 76 | 11 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W25 | 77 | 10 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W26 | 78 | 9 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W27 | 79 | 8 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 공정/부품 리드타임 지연
TWR_Z_096 | 2026W28 | 80 | 7 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W29 | 81 | 6 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W30 | 82 | 5 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W31 | 83 | 4 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W32 | 84 | 3 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W33 | 85 | 2 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_096 | 2026W34 | 86 | 1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W35 | 87 | 0 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
TWR_Z_096 | 2026W36 | 88 | -1 | 2026W35 | 2026W35 | 2026-08-31 | 2026W41 | 2026-10-12 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
WASH_F_097 | 2026W22 | 74 | 12 | 2026W34 | 2026W34 | 2026-08-24 | 2026W33 | 2026-08-17 |  | 0 | -1 | 정상
WASH_F_097 | 2026W23 | 75 | 11 | 2026W34 | 2026W34 | 2026-08-24 | 2026W33 | 2026-08-17 |  | 0 | -1 | 정상
WASH_F_097 | 2026W24 | 76 | 10 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W25 | 77 | 9 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W26 | 78 | 8 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W27 | 79 | 7 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W28 | 80 | 6 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W29 | 81 | 5 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W30 | 82 | 4 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W31 | 83 | 3 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W32 | 84 | 2 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W33 | 85 | 1 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W34 | 86 | 0 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W35 | 87 | -1 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_F_097 | 2026W36 | 88 | -2 | 2026W34 | 2026W34 | 2026-08-24 | 2026W34 | 2026-08-24 |  | 0 | 0 | 정상
WASH_T_098 | 2026W14 | 66 | 12 | 2026W26 | 2026W26 | 2026-06-29 | 2026W27 | 2026-07-06 | 2026W28 | 0 | 1 | 정상
WASH_T_098 | 2026W15 | 67 | 11 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_098 | 2026W16 | 68 | 10 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_098 | 2026W17 | 69 | 9 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_098 | 2026W18 | 70 | 8 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_098 | 2026W19 | 71 | 7 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 개발검증(DV) 지연 요소
WASH_T_098 | 2026W20 | 72 | 6 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 양산검증(PV) 지연 요소
WASH_T_098 | 2026W21 | 73 | 5 | 2026W26 | 2026W26 | 2026-06-29 | 2026W28 | 2026-07-13 | 2026W28 | 0 | 2 | 주의 | 공정/부품 리드타임 지연
WASH_T_098 | 2026W22 | 74 | 6 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W23 | 75 | 5 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W24 | 76 | 4 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W25 | 77 | 3 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W26 | 78 | 2 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W27 | 79 | 1 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W28 | 80 | 0 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W29 | 81 | -1 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
WASH_T_098 | 2026W30 | 82 | -2 | 2026W26 | 2026W28 | 2026-07-13 | 2026W28 | 2026-07-13 | 2026W28 | 2 | 0 | 정상
DRY_X_099 | 2026W31 | 83 | 12 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_099 | 2026W32 | 84 | 11 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_099 | 2026W33 | 85 | 10 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_099 | 2026W34 | 86 | 9 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_099 | 2026W35 | 87 | 8 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 개발검증(DV) 지연 요소
DRY_X_099 | 2026W36 | 88 | 7 | 2026W43 | 2026W43 | 2026-10-26 | 2026W49 | 2026-12-07 |  | 0 | 6 | 심각 | 양산검증(PV) 지연 요소
TWR_Z_100 | 2025W41 | 41 | 12 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W42 | 42 | 11 | 2026W01 | 2026W01 | 2026-01-05 | 2025W52 | 2025-12-29 | 2026W01 | 0 | -1 | 정상
TWR_Z_100 | 2025W43 | 43 | 10 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W44 | 44 | 9 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W45 | 45 | 8 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W46 | 46 | 7 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W47 | 47 | 6 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W48 | 48 | 5 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W49 | 49 | 4 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W50 | 50 | 3 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W51 | 51 | 2 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2025W52 | 52 | 1 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2026W01 | 53 | 0 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2026W02 | 54 | -1 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상
TWR_Z_100 | 2026W03 | 55 | -2 | 2026W01 | 2026W01 | 2026-01-05 | 2026W01 | 2026-01-05 | 2026W01 | 0 | 0 | 정상

## D12_SalesLoss
MODEL_CODE | SUBSIDIARY_CODE | LOSS_TYPE | LOSS_BASIS | ANCHOR_PLAN_WEEK | WINDOW_START_WEEK | WINDOW_END_WEEK | NPI_TARGET_AMT_KUSD | NPI_RESULT_AMT_KUSD | NPI_LOSS_AMT_KUSD | EOL_MODEL_CODE | EOL_DEFENSE_AMT_KUSD | NET_LOSS_AMT_KUSD
WASH_F_001 | VG03 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 0 | 91 | 0 |  | 0 | 0
WASH_F_001 | VG11 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 0 | 125.4 | 0 | DRY_X_019 | 0 | 0
WASH_T_002 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 |  | 0 | 0
WASH_T_002 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 |  | 0 | 0
WASH_T_002 | VG01 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 |  | 0 | 0
WASH_T_002 | VG01 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 |  | 0 | 0
WASH_T_002 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | TWR_Z_100 | 0 | 0
WASH_T_002 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | TWR_Z_100 | 0 | 0
DRY_X_003 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_030 | 0 | 0
DRY_X_003 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_030 | 0 | 0
DRY_X_003 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | DRY_X_047 | 0 | 0
DRY_X_003 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | DRY_X_047 | 0 | 0
DRY_X_003 | VG01 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
DRY_X_003 | VG01 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
TWR_Z_004 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W42 | 0 | 0 | 0 |  | 0 | 0
TWR_Z_004 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 |  | 0 | 0
WASH_F_005 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_F_049 | 0 | 0
WASH_F_005 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_F_049 | 0 | 0
WASH_F_005 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_T_078 | 0 | 0
WASH_F_005 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_T_078 | 0 | 0
WASH_T_006 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_T_078 | 0 | 0
WASH_T_006 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W42 | 1298.1 | 0 | 1298.1 | WASH_T_078 | 0 | 1298.1
WASH_T_006 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_081 | 0 | 0
WASH_T_006 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W42 | 957.1 | 0 | 957.1 | WASH_F_081 | 0 | 957.1
DRY_X_007 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W36 | 146.9 | 0 | 146.9 |  | 0 | 146.9
DRY_X_007 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 151.8 | 0 | 151.8 |  | 0 | 151.8
DRY_X_007 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W36 | 39.3 | 0 | 39.3 | WASH_T_074 | 0 | 39.3
DRY_X_007 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 698.2 | 0 | 698.2 | WASH_T_074 | 0 | 698.2
DRY_X_007 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W36 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
DRY_X_007 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
TWR_Z_008 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 0 | 0 | 0 | WASH_T_070 | 0 | 0
TWR_Z_008 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W44 | 678.6 | 0 | 678.6 | WASH_T_070 | 0 | 678.6
WASH_F_009 | VG01 | 실적 | 실적 | 2026W05 | 2026W05 | 2026W13 | 0 | 290.6 | 0 | WASH_F_045 | 0 | 0
WASH_T_010 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | WASH_F_069 | 0 | 0
WASH_T_010 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 1694 | 0 | 1694 | WASH_F_069 | 0 | 1694
WASH_T_010 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | TWR_Z_012 | 0 | 0
WASH_T_010 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 504.7 | 0 | 504.7 | TWR_Z_012 | 0 | 504.7
WASH_T_010 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | DRY_X_087 | 0 | 0
WASH_T_010 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 0 | 0 | 0 | DRY_X_087 | 0 | 0
DRY_X_011 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_027 | 0 | 0
DRY_X_011 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_027 | 0 | 0
DRY_X_011 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_079 | 0 | 0
DRY_X_011 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_079 | 0 | 0
TWR_Z_012 | VG01 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 920.2 | 1038.1 | 0 | WASH_F_069 | 0 | 0
WASH_F_013 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | WASH_T_014 | 0 | 0
WASH_F_013 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 839.6 | 0 | 839.6 | WASH_T_014 | 0 | 839.6
WASH_F_013 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
WASH_F_013 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
WASH_F_013 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
WASH_F_013 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
WASH_T_014 | VG07 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 0 | 1022.3 | 0 | WASH_F_053 | 0 | 0
DRY_X_015 | VG01 | 실적 | 실적 | 2025W48 | 2025W48 | 2026W04 | 2003.1 | 819.4 | 1183.7 | TWR_Z_084 | 0 | 1183.7
TWR_Z_016 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W32 | 0 | 0 | 0 | WASH_T_094 | 0 | 0
TWR_Z_016 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W32 | 0 | 0 | 0 | WASH_T_094 | 0 | 0
WASH_F_017 | VG04 | 실적 | 실적 | 2025W51 | 2025W51 | 2026W07 | 0 | 639 | 0 | WASH_T_070 | 0 | 0
WASH_F_017 | VG05 | 실적 | 실적 | 2025W51 | 2025W51 | 2026W07 | 2545.1 | 0 | 2545.1 |  | 0 | 2545.1
WASH_T_018 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 232.6 | 0 | 232.6 | WASH_F_041 | 0 | 232.6
WASH_T_018 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W38 | 239 | 0 | 239 | WASH_F_041 | 0 | 239
WASH_T_018 | VG01 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 818.4 | 0 | 818.4 | TWR_Z_100 | 0 | 818.4
WASH_T_018 | VG01 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W38 | 844.3 | 0 | 844.3 | TWR_Z_100 | 0 | 844.3
WASH_T_018 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 1212.1 | 0 | 1212.1 | TWR_Z_036 | 0 | 1212.1
WASH_T_018 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W38 | 1230.4 | 0 | 1230.4 | TWR_Z_036 | 0 | 1230.4
DRY_X_019 | VG01 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 0 | 76.8 | 0 | WASH_T_014 | 0 | 0
DRY_X_019 | VG09 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 1171.8 | 1008.1 | 163.7 | TWR_Z_064 | 0 | 163.7
TWR_Z_020 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 | DRY_X_015 | 0 | 0
TWR_Z_020 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W48 | 0 | 0 | 0 | DRY_X_015 | 0 | 0
WASH_F_021 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_025 | 0 | 0
WASH_F_021 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_025 | 0 | 0
WASH_F_021 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
WASH_F_021 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
WASH_T_022 | VG05 | 실적 | 실적 | 2026W03 | 2026W03 | 2026W11 | 613.9 | 0 | 613.9 | DRY_X_031 | 0 | 613.9
DRY_X_023 | VG08 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 2052.9 | 0 | 2052.9 | DRY_X_083 | 0 | 2052.9
DRY_X_023 | VG04 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 980.3 | 0 | 980.3 | DRY_X_083 | 0 | 980.3
TWR_Z_024 | VG09 | 실적 | 실적 | 2026W07 | 2026W07 | 2026W15 | 2422.8 | 0 | 2422.8 | WASH_F_093 | 0 | 2422.8
WASH_F_025 | VG05 | 실적 | 실적 | 2026W07 | 2026W07 | 2026W15 | 1078.6 | 48.6 | 1030 | WASH_F_069 | 0 | 1030
WASH_F_025 | VG06 | 실적 | 실적 | 2026W07 | 2026W07 | 2026W15 | 0 | 0 | 0 | WASH_T_070 | 0 | 0
WASH_T_026 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | TWR_Z_036 | 0 | 0
WASH_T_026 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W38 | 0 | 0 | 0 | TWR_Z_036 | 0 | 0
WASH_T_026 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
WASH_T_026 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W38 | 1388.8 | 0 | 1388.8 | DRY_X_071 | 0 | 1388.8
DRY_X_027 | VG02 | 실적 | 실적 | 2026W01 | 2026W01 | 2026W09 | 0 | 0 | 0 | WASH_F_065 | 50.8 | 0
DRY_X_027 | VG01 | 실적 | 실적 | 2026W01 | 2026W01 | 2026W09 | 0 | 118.6 | 0 | TWR_Z_012 | 0 | 0
TWR_Z_028 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W36 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
TWR_Z_028 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W36 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
TWR_Z_028 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W36 | 0 | 0 | 0 | DRY_X_079 | 0 | 0
TWR_Z_028 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W36 | 0 | 0 | 0 | DRY_X_079 | 0 | 0
WASH_F_029 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
WASH_F_029 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W42 | 338.8 | 0 | 338.8 | WASH_T_062 | 0 | 338.8
WASH_F_029 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W38 | 0 | 0 | 0 |  | 0 | 0
WASH_F_029 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W42 | 1144.1 | 0 | 1144.1 |  | 0 | 1144.1
WASH_T_030 | VG01 | 실적 | 실적 | 2026W17 | 2026W17 | 2026W25 | 185.6 | 185.8 | 0 |  | 0 | 0
DRY_X_031 | VG11 | 실적 | 실적 | 2025W51 | 2025W51 | 2026W07 | 0 | 190.1 | 0 | DRY_X_075 | 0 | 0
TWR_Z_032 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 350.1 | 0 | 350.1 | TWR_Z_100 | 0 | 350.1
TWR_Z_032 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W45 | 434.4 | 0 | 434.4 | TWR_Z_100 | 0 | 434.4
TWR_Z_032 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | TWR_Z_036 | 0 | 0
TWR_Z_032 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W45 | 155.1 | 0 | 155.1 | TWR_Z_036 | 0 | 155.1
TWR_Z_032 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | DRY_X_031 | 0 | 0
TWR_Z_032 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W45 | 923.4 | 0 | 923.4 | DRY_X_031 | 0 | 923.4
WASH_F_033 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 |  | 0 | 0
WASH_F_033 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 675.9 | 0 | 675.9 |  | 0 | 675.9
WASH_F_033 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | WASH_T_054 | 0 | 0
WASH_F_033 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 678 | 0 | 678 | WASH_T_054 | 0 | 678
WASH_T_034 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
WASH_T_034 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
DRY_X_035 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | WASH_F_001 | 0 | 0
DRY_X_035 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 908.3 | 0 | 908.3 | WASH_F_001 | 0 | 908.3
DRY_X_035 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_019 | 0 | 0
DRY_X_035 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 161.9 | 0 | 161.9 | DRY_X_019 | 0 | 161.9
DRY_X_035 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 | DRY_X_031 | 0 | 0
DRY_X_035 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | DRY_X_031 | 0 | 0
TWR_Z_036 | VG04 | 실적 | 실적 | 2025W41 | 2025W41 | 2025W49 | 0 | 462.1 | 0 |  | 0 | 0
TWR_Z_036 | VG09 | 실적 | 실적 | 2025W41 | 2025W41 | 2025W49 | 0 | 142.1 | 0 | DRY_X_019 | 0 | 0
TWR_Z_036 | VG11 | 실적 | 실적 | 2025W41 | 2025W41 | 2025W49 | 0 | 213.2 | 0 | WASH_T_094 | 0 | 0
WASH_F_037 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | TWR_Z_036 | 0 | 0
WASH_F_037 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 314.1 | 0 | 314.1 | TWR_Z_036 | 0 | 314.1
WASH_F_037 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 292.1 | 0 | 292.1 | DRY_X_019 | 0 | 292.1
WASH_F_037 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 782.1 | 0 | 782.1 | DRY_X_019 | 0 | 782.1
WASH_F_037 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
WASH_F_037 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
WASH_T_038 | VG01 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 0 | 0 | 0 | DRY_X_031 | 0 | 0
DRY_X_039 | VG12 | 실적 | 실적 | 2026W11 | 2026W11 | 2026W19 | 853.8 | 443.9 | 409.9 |  | 0 | 409.9
TWR_Z_040 | VG10 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 388.3 | 496.9 | 0 | WASH_T_038 | 0 | 0
TWR_Z_040 | VG04 | 실적 | 실적 | 2025W47 | 2025W47 | 2026W03 | 0 | 125.7 | 0 | WASH_F_093 | 0 | 0
WASH_F_041 | VG11 | 실적 | 실적 | 2026W18 | 2026W18 | 2026W26 | 589.3 | 0 | 589.3 |  | 0 | 589.3
WASH_T_042 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 259.8 | 0 | 259.8 | WASH_T_014 | 0 | 259.8
WASH_T_042 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 280.1 | 0 | 280.1 | WASH_T_014 | 0 | 280.1
WASH_T_042 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
WASH_T_042 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
DRY_X_043 | VG04 | 실적 | 실적 | 2026W09 | 2026W09 | 2026W17 | 286.2 | 0 | 286.2 | WASH_F_041 | 0 | 286.2
DRY_X_043 | VG07 | 실적 | 실적 | 2026W09 | 2026W09 | 2026W17 | 326.3 | 520.5 | 0 | WASH_T_086 | 0 | 0
DRY_X_043 | VG08 | 실적 | 실적 | 2026W09 | 2026W09 | 2026W17 | 0 | 679.3 | 0 | WASH_F_065 | 0 | 0
TWR_Z_044 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
TWR_Z_044 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
TWR_Z_044 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_F_041 | 0 | 0
TWR_Z_044 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_F_041 | 0 | 0
WASH_F_045 | VG11 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 727.2 | 429.6 | 297.6 | WASH_T_098 | 0 | 297.6
WASH_T_046 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
WASH_T_046 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
DRY_X_047 | VG01 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 0 | 503.1 | 0 | WASH_T_030 | 0 | 0
TWR_Z_048 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 838.4 | 0 | 838.4 | DRY_X_023 | 0 | 838.4
TWR_Z_048 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W44 | 2241.8 | 0 | 2241.8 | DRY_X_023 | 0 | 2241.8
WASH_F_049 | VG03 | 실적 | 실적 | 2026W05 | 2026W05 | 2026W13 | 0 | 97.5 | 0 | TWR_Z_100 | 1979.7 | 0
WASH_T_050 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 79.1 | 0 | 79.1 | WASH_T_062 | 0 | 79.1
WASH_T_050 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W39 | 1301.7 | 0 | 1301.7 | WASH_T_062 | 0 | 1301.7
WASH_T_050 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_F_073 | 0 | 0
WASH_T_050 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | WASH_F_073 | 0 | 0
WASH_T_050 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W33 | 0 | 0 | 0 | WASH_T_086 | 0 | 0
WASH_T_050 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W39 | 366.2 | 0 | 366.2 | WASH_T_086 | 0 | 366.2
DRY_X_051 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | TWR_Z_024 | 0 | 0
DRY_X_051 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 248.8 | 0 | 248.8 | TWR_Z_024 | 0 | 248.8
DRY_X_051 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | WASH_T_094 | 0 | 0
DRY_X_051 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 816.7 | 0 | 816.7 | WASH_T_094 | 0 | 816.7
DRY_X_051 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W39 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
DRY_X_051 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
TWR_Z_052 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W34 | 77.6 | 0 | 77.6 | WASH_F_065 | 0 | 77.6
TWR_Z_052 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W34 | 73.8 | 0 | 73.8 | WASH_F_065 | 0 | 73.8
TWR_Z_052 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W34 | 0 | 0 | 0 | WASH_F_045 | 0 | 0
TWR_Z_052 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W34 | 0 | 0 | 0 | WASH_F_045 | 0 | 0
WASH_F_053 | VG01 | 실적 | 실적 | 2025W48 | 2025W48 | 2026W04 | 0 | 100.2 | 0 |  | 0 | 0
WASH_T_054 | VG05 | 실적 | 실적 | 2025W48 | 2025W48 | 2026W04 | 0 | 9.1 | 0 |  | 0 | 0
DRY_X_055 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 | DRY_X_067 | 0 | 0
DRY_X_055 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W47 | 0 | 0 | 0 | DRY_X_067 | 0 | 0
DRY_X_055 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 |  | 0 | 0
DRY_X_055 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W47 | 184.5 | 0 | 184.5 |  | 0 | 184.5
TWR_Z_056 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | DRY_X_043 | 0 | 0
TWR_Z_056 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | DRY_X_043 | 0 | 0
TWR_Z_056 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
TWR_Z_056 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
TWR_Z_056 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_094 | 0 | 0
TWR_Z_056 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_094 | 0 | 0
WASH_F_057 | VG05 | 실적 | 실적 | 2025W42 | 2025W42 | 2025W50 | 0 | 599 | 0 | WASH_T_074 | 0 | 0
WASH_F_057 | VG08 | 실적 | 실적 | 2025W42 | 2025W42 | 2025W50 | 218.4 | 0 | 218.4 | TWR_Z_012 | 0 | 218.4
WASH_T_058 | VG08 | 실적 | 실적 | 2025W42 | 2025W42 | 2025W50 | 0 | 150.8 | 0 |  | 0 | 0
WASH_T_058 | VG03 | 실적 | 실적 | 2025W42 | 2025W42 | 2025W50 | 0 | 326.5 | 0 | TWR_Z_064 | 0 | 0
DRY_X_059 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_038 | 0 | 0
DRY_X_059 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 0 | 0 | 0 | WASH_T_038 | 0 | 0
DRY_X_059 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 450.7 | 0 | 450.7 | WASH_T_014 | 0 | 450.7
DRY_X_059 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 1206 | 0 | 1206 | WASH_T_014 | 0 | 1206
DRY_X_059 | VG07 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 320.9 | 0 | 320.9 | WASH_T_022 | 0 | 320.9
DRY_X_059 | VG07 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 995.1 | 0 | 995.1 | WASH_T_022 | 0 | 995.1
TWR_Z_060 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_T_062 | 0 | 0
TWR_Z_060 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 1053 | 0 | 1053 | WASH_T_062 | 0 | 1053
TWR_Z_060 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 |  | 0 | 0
TWR_Z_060 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 0 | 0 | 0 |  | 0 | 0
WASH_F_061 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 |  | 0 | 0
WASH_F_061 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 35 | 0 | 35 |  | 0 | 35
WASH_F_061 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 1122.6 | 0 | 1122.6 |  | 0 | 1122.6
WASH_F_061 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 2161.2 | 0 | 2161.2 |  | 0 | 2161.2
WASH_F_061 | VG05 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
WASH_F_061 | VG05 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 668.7 | 0 | 668.7 | WASH_F_093 | 0 | 668.7
WASH_T_062 | VG10 | 실적 | 실적 | 2026W16 | 2026W16 | 2026W24 | 522.1 | 0 | 522.1 | WASH_T_070 | 0 | 522.1
DRY_X_063 | VG06 | 실적 | 실적 | 2025W52 | 2025W52 | 2026W08 | 232.6 | 0 | 232.6 | WASH_F_017 | 0 | 232.6
DRY_X_063 | VG02 | 실적 | 실적 | 2025W52 | 2025W52 | 2026W08 | 595 | 236.1 | 358.9 | TWR_Z_040 | 0 | 358.9
DRY_X_063 | VG07 | 실적 | 실적 | 2025W52 | 2025W52 | 2026W08 | 1037.1 | 0 | 1037.1 | WASH_T_022 | 0 | 1037.1
TWR_Z_064 | VG04 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 204.9 | 159.5 | 45.4 |  | 0 | 45.4
TWR_Z_064 | VG01 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 1055.7 | 86.6 | 969.1 |  | 0 | 969.1
WASH_F_065 | VG07 | 실적 | 실적 | 2025W46 | 2025W46 | 2026W02 | 647.9 | 112.6 | 535.3 | WASH_F_081 | 0 | 535.3
WASH_F_065 | VG02 | 실적 | 실적 | 2025W46 | 2025W46 | 2026W02 | 219.6 | 228.7 | 0 | DRY_X_087 | 0 | 0
WASH_T_066 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W42 | 0 | 0 | 0 | DRY_X_071 | 0 | 0
WASH_T_066 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W48 | 1062.9 | 0 | 1062.9 | DRY_X_071 | 0 | 1062.9
WASH_T_066 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W42 | 0 | 0 | 0 | WASH_F_041 | 0 | 0
WASH_T_066 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W48 | 1317.8 | 0 | 1317.8 | WASH_F_041 | 0 | 1317.8
WASH_T_066 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W42 | 0 | 0 | 0 | DRY_X_063 | 0 | 0
WASH_T_066 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W48 | 1995.3 | 0 | 1995.3 | DRY_X_063 | 0 | 1995.3
DRY_X_067 | VG03 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 222.2 | 372.5 | 0 |  | 0 | 0
DRY_X_067 | VG10 | 실적 | 실적 | 2025W44 | 2025W44 | 2025W52 | 310.2 | 0 | 310.2 | DRY_X_071 | 0 | 310.2
TWR_Z_068 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | DRY_X_019 | 0 | 0
TWR_Z_068 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 469.8 | 0 | 469.8 | DRY_X_019 | 0 | 469.8
TWR_Z_068 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_073 | 0 | 0
TWR_Z_068 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 0 | 0 | 0 | WASH_F_073 | 0 | 0
WASH_F_069 | VG08 | 실적 | 실적 | 2025W43 | 2025W43 | 2025W51 | 857.6 | 328.4 | 529.2 | TWR_Z_040 | 0 | 529.2
WASH_F_069 | VG06 | 실적 | 실적 | 2025W43 | 2025W43 | 2025W51 | 0 | 235 | 0 | TWR_Z_076 | 0 | 0
WASH_F_069 | VG07 | 실적 | 실적 | 2025W43 | 2025W43 | 2025W51 | 0 | 521.1 | 0 | DRY_X_023 | 0 | 0
WASH_T_070 | VG08 | 실적 | 실적 | 2026W16 | 2026W16 | 2026W24 | 890 | 183.7 | 706.3 |  | 0 | 706.3
DRY_X_071 | VG08 | 실적 | 실적 | 2025W43 | 2025W43 | 2025W51 | 619.6 | 962.9 | 0 | TWR_Z_024 | 0 | 0
TWR_Z_072 | VG10 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
TWR_Z_072 | VG10 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_093 | 0 | 0
TWR_Z_072 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_001 | 0 | 0
TWR_Z_072 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_F_001 | 0 | 0
WASH_F_073 | VG09 | 실적 | 실적 | 2026W02 | 2026W02 | 2026W10 | 1684.2 | 1074.8 | 609.4 | TWR_Z_040 | 0 | 609.4
WASH_F_073 | VG12 | 실적 | 실적 | 2026W02 | 2026W02 | 2026W10 | 0 | 124.9 | 0 | WASH_F_025 | 0 | 0
WASH_T_074 | VG01 | 실적 | 실적 | 2026W17 | 2026W17 | 2026W25 | 210.7 | 131 | 79.7 | DRY_X_043 | 0 | 79.7
DRY_X_075 | VG01 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 1021.9 | 1243.6 | 0 |  | 0 | 0
TWR_Z_076 | VG10 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 0 | 712.4 | 0 | WASH_T_062 | 0 | 0
TWR_Z_076 | VG03 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 213.1 | 0 | 213.1 | WASH_F_065 | 0 | 213.1
WASH_F_077 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | WASH_T_070 | 0 | 0
WASH_F_077 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W45 | 194 | 0 | 194 | WASH_T_070 | 0 | 194
WASH_F_077 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W41 | 0 | 0 | 0 | TWR_Z_040 | 0 | 0
WASH_F_077 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W45 | 1156.2 | 0 | 1156.2 | TWR_Z_040 | 0 | 1156.2
WASH_T_078 | VG02 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 1591.2 | 302.6 | 1288.6 | DRY_X_083 | 0 | 1288.6
DRY_X_079 | VG12 | 실적 | 실적 | 2026W14 | 2026W14 | 2026W22 | 882.9 | 270 | 612.9 | WASH_F_045 | 0 | 612.9
DRY_X_079 | VG07 | 실적 | 실적 | 2026W14 | 2026W14 | 2026W22 | 1715.9 | 0 | 1715.9 | WASH_T_058 | 0 | 1715.9
DRY_X_079 | VG09 | 실적 | 실적 | 2026W14 | 2026W14 | 2026W22 | 614 | 0 | 614 | DRY_X_031 | 0 | 614
TWR_Z_080 | VG12 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 | WASH_F_053 | 0 | 0
TWR_Z_080 | VG12 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 | WASH_F_053 | 0 | 0
WASH_F_081 | VG04 | 실적 | 실적 | 2025W48 | 2025W48 | 2026W04 | 1655.6 | 0 | 1655.6 |  | 0 | 1655.6
WASH_F_081 | VG03 | 실적 | 실적 | 2025W48 | 2025W48 | 2026W04 | 1065.4 | 882.6 | 182.8 |  | 0 | 182.8
WASH_T_082 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W44 | 0 | 0 | 0 | WASH_F_041 | 0 | 0
WASH_T_082 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 579.5 | 0 | 579.5 | WASH_F_041 | 0 | 579.5
DRY_X_083 | VG05 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 1480.9 | 171.4 | 1309.5 | WASH_T_058 | 0 | 1309.5
TWR_Z_084 | VG04 | 실적 | 실적 | 2026W04 | 2026W04 | 2026W12 | 0 | 317.6 | 0 | WASH_F_045 | 0 | 0
TWR_Z_084 | VG06 | 실적 | 실적 | 2026W04 | 2026W04 | 2026W12 | 0 | 487.4 | 0 | WASH_T_062 | 0 | 0
TWR_Z_084 | VG01 | 실적 | 실적 | 2026W04 | 2026W04 | 2026W12 | 1855.5 | 455.7 | 1399.8 | DRY_X_031 | 0 | 1399.8
WASH_F_085 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 1296.1 | 0 | 1296.1 | DRY_X_067 | 0 | 1296.1
WASH_F_085 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 1167.7 | 0 | 1167.7 | DRY_X_067 | 0 | 1167.7
WASH_F_085 | VG01 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_T_078 | 0 | 0
WASH_F_085 | VG01 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_T_078 | 0 | 0
WASH_T_086 | VG07 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 515.5 | 508.1 | 7.4 | DRY_X_075 | 0 | 7.4
WASH_T_086 | VG01 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 689.3 | 0 | 689.3 | TWR_Z_088 | 0 | 689.3
WASH_T_086 | VG09 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 1110.8 | 538.9 | 571.9 |  | 0 | 571.9
DRY_X_087 | VG12 | 실적 | 실적 | 2026W12 | 2026W12 | 2026W20 | 410.5 | 61.9 | 348.6 | DRY_X_063 | 0 | 348.6
TWR_Z_088 | VG11 | 실적 | 실적 | 2026W22 | 2026W22 | 2026W30 | 181.6 | 356 | 0 |  | 0 | 0
TWR_Z_088 | VG06 | 실적 | 실적 | 2026W22 | 2026W22 | 2026W30 | 1848.5 | 799.1 | 1049.4 | DRY_X_075 | 0 | 1049.4
TWR_Z_088 | VG07 | 실적 | 실적 | 2026W22 | 2026W22 | 2026W30 | 1145.8 | 276.5 | 869.3 | WASH_F_093 | 0 | 869.3
WASH_F_089 | VG08 | 실적 | 실적 | 2026W15 | 2026W15 | 2026W23 | 372.9 | 165.9 | 207 |  | 0 | 207
WASH_T_090 | VG06 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 1158.8 | 0 | 1158.8 | TWR_Z_088 | 0 | 1158.8
WASH_T_090 | VG06 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 1262.8 | 0 | 1262.8 | TWR_Z_088 | 0 | 1262.8
WASH_T_090 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W40 | 913 | 0 | 913 | WASH_F_065 | 0 | 913
WASH_T_090 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W40 | 967.5 | 0 | 967.5 | WASH_F_065 | 0 | 967.5
DRY_X_091 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W42 | 0 | 0 | 0 |  | 0 | 0
DRY_X_091 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W46 | 723.1 | 0 | 723.1 |  | 0 | 723.1
TWR_Z_092 | VG11 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | DRY_X_047 | 0 | 0
TWR_Z_092 | VG11 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 1940 | 0 | 1940 | DRY_X_047 | 0 | 1940
TWR_Z_092 | VG02 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W37 | 0 | 0 | 0 | WASH_T_074 | 0 | 0
TWR_Z_092 | VG02 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W43 | 517.7 | 0 | 517.7 | WASH_T_074 | 0 | 517.7
WASH_F_093 | VG03 | 실적 | 실적 | 2026W16 | 2026W16 | 2026W24 | 0 | 332.6 | 0 | DRY_X_015 | 0 | 0
WASH_F_093 | VG05 | 실적 | 실적 | 2026W16 | 2026W16 | 2026W24 | 0 | 120.9 | 0 |  | 0 | 0
WASH_T_094 | VG03 | 실적 | 실적 | 2026W03 | 2026W03 | 2026W11 | 649.9 | 180.1 | 469.8 | WASH_T_062 | 0 | 469.8
WASH_T_094 | VG01 | 실적 | 실적 | 2026W03 | 2026W03 | 2026W11 | 640.1 | 255.5 | 384.6 | TWR_Z_024 | 0 | 384.6
WASH_T_094 | VG07 | 실적 | 실적 | 2026W03 | 2026W03 | 2026W11 | 896.9 | 412.8 | 484.1 | WASH_T_070 | 0 | 484.1
DRY_X_095 | VG08 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W34 | 0 | 0 | 0 | WASH_F_017 | 0 | 0
DRY_X_095 | VG08 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W34 | 0 | 0 | 0 | WASH_F_017 | 0 | 0
TWR_Z_096 | VG09 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W35 | 0 | 0 | 0 |  | 0 | 0
TWR_Z_096 | VG09 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W41 | 871.8 | 0 | 871.8 |  | 0 | 871.8
WASH_F_097 | VG03 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W34 | 252.2 | 0 | 252.2 | WASH_T_098 | 0 | 252.2
WASH_F_097 | VG03 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W34 | 271.3 | 0 | 271.3 | WASH_T_098 | 0 | 271.3
WASH_F_097 | VG04 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W34 | 346.7 | 0 | 346.7 | WASH_T_098 | 0 | 346.7
WASH_F_097 | VG04 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W34 | 333 | 0 | 333 | WASH_T_098 | 0 | 333
WASH_T_098 | VG03 | 실적 | 실적 | 2026W20 | 2026W20 | 2026W28 | 908.7 | 91.2 | 817.5 | WASH_T_022 | 0 | 817.5
WASH_T_098 | VG01 | 실적 | 실적 | 2026W20 | 2026W20 | 2026W28 | 339.3 | 58.7 | 280.6 | WASH_T_054 | 0 | 280.6
DRY_X_099 | VG01 | 예상 | 시스템 | 2026W36 | 2026W36 | 2026W43 | 615.4 | 0 | 615.4 | TWR_Z_088 | 0 | 615.4
DRY_X_099 | VG01 | 예상 | 이상감지 | 2026W36 | 2026W36 | 2026W49 | 4093.2 | 0 | 4093.2 | TWR_Z_088 | 0 | 4093.2
TWR_Z_100 | VG03 | 실적 | 실적 | 2025W45 | 2025W45 | 2026W01 | 583.4 | 960 | 0 | TWR_Z_088 | 0 | 0